## BBP 4 - TCR-Tool
IM | ID | Section | Direction | Line |  | Year |  | Week |  | Period from |  | Period to |  | Duration | Time of day | Reason for restriction | Traffic impact |  |  |  |  | Traffic measures |  |  |  |  | Description | International coordination | In yearly timetable | IM Project ID (Optional) | Last updated | Classification | Weekdays | Interval | Affected estimated travel volume | Affected border | Deviation location | Deviation border | Status | Additional information | Automatic process
|  |  |  | From | To | From | To | From | To | Date from | Time from | Date to | Time to |  |  |  | Total closure | Reduced Track Availability | Speed Restrictions | Weight, Length, Profile | Diesel only | Cancellation | Re-routing | Train replacement | Delay | Other
DB Netz AG | 24435472CE0D2.01 | Mainz Hbf - Mannheim Hbf | < > | Mannheim Hbf | Mannheim Hbf | 2022 | 2022 | 2 | 3 | 2022-01-15 21:00 | 21:00 | 2022-01-17 05:00 | 5:00 | 1 d, 08 h | continuous | Bridge |  | ST | [8 empty] | Brückenarbeiten Erneuerung EÜ Tunnelstraße Mannheim in Mannheim Hbf |  | N | 306073.01 | 2021-06-18 10:56 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 24435472CE0D2.02 | Mainz Hbf - Mannheim Hbf | < > | Mannheim Hbf | Mannheim Hbf | 2022 | 2022 | 2 | 3 | 2022-01-15 21:00 | 21:00 | 2022-01-17 05:00 | 5:00 | 1 d, 08 h | continuous | Bridge |  | ST | [8 empty] | Brückenarbeiten Erneuerung EÜ Tunnelstraße Mannheim in Mannheim Hbf |  | N | 306073.02 | 2021-06-18 10:56 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 247256243E5B2.03 | Mainz Hbf - Mannheim Hbf | < > | Mannheim Hbf | Mannheim Hbf | 2022 | 2022 | 6 | 49 | 2022-02-08 | 0:00 | 2022-12-10 23:59 | 23:59 | 306 d | continuous | Bridge |  | ST | [8 empty] | Brückenarbeiten Erneuerung EÜ Tunnelstraße Mannheim |  | N | 306157.03 | 2021-07-20 18:11 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 24A36855BDAD2.01 | Mainz Hbf - Mannheim Hbf | < > | Mannheim Hbf | Mannheim Hbf | 2022 | 2022 | 11 | 11 | 2022-03-14 21:00 | 21:00 | 2022-03-16 21:00 | 21:00 | 2 d | continuous | Bridge |  | ST | [8 empty] | Brückenarbeiten Erneuerung EÜ Tunnelstraße Mannheim, Bauphase 1.1.1 A+B / 1.1.2 A in Mannheim Hbf |  | N | 306297.01 | 2021-08-23 11:30 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 24A36855BDAD2.03 | Mainz Hbf - Mannheim Hbf | < > | Mannheim Hbf | Mannheim Hbf | 2022 | 2022 | 11 | 11 | 2022-03-16 21:00 | 21:00 | 2022-03-18 21:00 | 21:00 | 2 d | continuous | Bridge |  | ST | [8 empty] | Brückenarbeiten Erneuerung EÜ Tunnelstraße Mannheim, Bauphase 1.1.1 A+B / 1.1.2 A in Mannheim Hbf |  | N | 306297.03 | 2021-08-23 11:30 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 24A36855BDAD2.05 | Mainz Hbf - Mannheim Hbf | < > | Mannheim Hbf | Mannheim Hbf | 2022 | 2022 | 11 | 11 | 2022-03-18 21:00 | 21:00 | 2022-03-20 21:00 | 21:00 | 2 d | continuous | Bridge |  | ST | [8 empty] | Brückenarbeiten Erneuerung EÜ Tunnelstraße Mannheim, Bauphase 1.1.1 A+B / 1.1.2 A in Mannheim Hbf |  | N | 306297.05 | 2021-08-23 11:30 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 24A36D22D61D2.02 | Mainz Hbf - Mannheim Hbf | < > | Mannheim Hbf | Mannheim Hbf | 2022 | 2022 | 11 | 12 | 2022-03-20 21:00 | 21:00 | 2022-03-22 21:00 | 21:00 | 2 d | continuous | Bridge |  | ST | [8 empty] | Brückenarbeiten Erneuerung EÜ Tunnelstraße Mannheim, Bauphase 1.1.2 A+B / 1.1.3 |  | N | 306324.02 | 2021-08-23 11:49 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 21E447E03BBEC.01 | Mainz Hbf - Mannheim Hbf | < > | Mannheim Hbf | Mannheim Hbf | 2022 | 2022 | 18 | 19 | 2022-05-04 | 0:00 | 2022-05-10 04:00 | 4:00 | 6 d, 04 h | continuous | Bridge |  | ST | [8 empty] | Brückenarbeiten Erneuerung EÜ Tunnelstraße Mannheim |  | N | 306591.01 | 2020-04-27 07:04 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 21E447E03BBEC.03 | Mainz Hbf - Mannheim Hbf | < > | Mannheim Hbf | Mannheim Hbf | 2022 | 2022 | 19 | 19 | 2022-05-10 | 0:00 | 2022-05-13 04:00 | 4:00 | 3 d, 04 h | continuous | Bridge |  | ST | [8 empty] | Brückenarbeiten Erneuerung EÜ Tunnelstraße Mannheim |  | N | 306591.03 | 2020-04-27 07:04 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 21E447E03BBEC.05 | Mainz Hbf - Mannheim Hbf | < > | Mannheim Hbf | Mannheim Hbf | 2022 | 2022 | 19 | 20 | 2022-05-13 | 0:00 | 2022-05-16 04:00 | 4:00 | 3 d, 04 h | continuous | Bridge |  | ST | [8 empty] | Brückenarbeiten Erneuerung EÜ Tunnelstraße Mannheim |  | N | 306591.05 | 2020-04-27 07:04 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 21E44B41E230C.01 | Mainz Hbf - Mannheim Hbf | < > | Mannheim Hbf | Mannheim Hbf | 2022 | 2022 | 35 | 39 | 2022-09-02 22:45 | 22:45 | 2022-09-26 04:00 | 4:00 | 8 d, 21 h | periodical | Bridge |  | ST | [8 empty] | Brückenarbeiten Erneuerung EÜ Tunnelstraße Mannheim |  | N | 306196.01 | 2020-04-27 07:17 |  | 5,6,7 | 1
DB Netz AG | 21E44B8B81D8C.01 | Mainz Hbf - Mannheim Hbf | < > | Mannheim Hbf | Mannheim Hbf | 2022 | 2022 | 39 | 42 | 2022-09-26 04:00 | 4:00 | 2022-10-17 04:00 | 4:00 | 21 d | continuous | Bridge |  | ST | [8 empty] | Brückenarbeiten Erneuerung EÜ Tunnelstraße Mannheim |  | N | 306306.01 | 2020-08-13 13:05 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 21E44B8B81D8C.02 | Mainz Hbf - Mannheim Hbf | < > | Mannheim Hbf | Mannheim Hbf | 2022 | 2022 | 39 | 42 | 2022-09-30 22:45 | 22:45 | 2022-10-17 04:00 | 4:00 | 6 d, 16 h | periodical | Bridge |  | ST | [8 empty] | Brückenarbeiten Erneuerung EÜ Tunnelstraße Mannheim |  | N | 306306.02 | 2020-08-13 13:05 |  | 5,6,7 | 1
DB Netz AG | 21E44B8B81D8C.03 | Mainz Hbf - Mannheim Hbf | < > | Mannheim Hbf | Mannheim Hbf | 2022 | 2022 | 41 | 42 | 2022-10-15 22:45 | 22:45 | 2022-10-17 04:00 | 4:00 | 1 d, 05 h | continuous | Bridge |  | ST | [8 empty] | Brückenarbeiten Erneuerung EÜ Tunnelstraße Mannheim |  | N | 306306.03 | 2020-08-13 13:05 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 21E44B8B81D8C.04 | Mainz Hbf - Mannheim Hbf | < > | Mannheim Hbf | Mannheim Hbf | 2022 | 2022 | 42 | 42 | 2022-10-17 04:00 | 4:00 | 2022-10-21 04:00 | 4:00 | 4 d | continuous | Bridge |  | ST | [8 empty] | Brückenarbeiten Erneuerung EÜ Tunnelstraße Mannheim |  | N | 306306.04 | 2020-08-13 13:05 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 21E44BCB7FAEC.01 | Mainz Hbf - Mannheim Hbf | < > | Mannheim Hbf | Mannheim Hbf | 2022 | 2022 | 42 | 43 | 2022-10-21 22:45 | 22:45 | 2022-10-24 04:00 | 4:00 | 2 d, 05 h | continuous | Bridge |  | ST | [8 empty] | Brückenarbeiten Erneuerung EÜ Tunnelstraße Mannheim |  | N | 306407.01 | 2020-04-27 07:19 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 21E44BDE927EC.01 | Mainz Hbf - Mannheim Hbf | < > | Mannheim Hbf | Mannheim Hbf | 2022 | 2022 | 43 | 44 | 2022-10-28 22:45 | 22:45 | 2022-10-31 04:00 | 4:00 | 2 d, 05 h | continuous | Bridge |  | ST | [8 empty] | Brückenarbeiten Erneuerung EÜ Tunnelstraße Mannheim |  | N | 306518.01 | 2020-04-27 07:19 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 21E44BE64C08C.01 | Mainz Hbf - Mannheim Hbf | < > | Mannheim Hbf | Mannheim Hbf | 2022 | 2022 | 44 | 45 | 2022-11-04 22:45 | 22:45 | 2022-11-07 04:00 | 4:00 | 2 d, 05 h | continuous | Bridge |  | ST | [8 empty] | Brückenarbeiten Erneuerung EÜ Tunnelstraße Mannheim |  | N | 306454.01 | 2020-04-27 07:19 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 21E44BFEB608C.01 | Mainz Hbf - Mannheim Hbf | < > | Mannheim Hbf | Mannheim Hbf | 2022 | 2022 | 45 | 46 | 2022-11-11 22:45 | 22:45 | 2022-11-14 04:00 | 4:00 | 2 d, 05 h | continuous | Bridge |  | ST | [8 empty] | Brückenarbeiten Erneuerung EÜ Tunnelstraße Mannheim |  | N | 306493.01 | 2020-04-27 07:20 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 21E44C0B4CB0C.01 | Mainz Hbf - Mannheim Hbf | < > | Mannheim Hbf | Mannheim Hbf | 2022 | 2022 | 46 | 47 | 2022-11-18 22:45 | 22:45 | 2022-11-21 04:00 | 4:00 | 2 d, 05 h | continuous | Bridge |  | ST | [8 empty] | Brückenarbeiten Erneuerung EÜ Tunnelstraße Mannheim |  | N | 306514.01 | 2020-04-27 07:20 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 247A64135A948.02 | Saarbrücken Grenze - Ludwigshafen (Rhein) Überleitung Süd | < | Weidenthal | Hochspeyer Ost | 2022 | 2022 | 7 | 8 | 2022-02-20 21:00 | 21:00 | 2022-02-25 05:00 | 5:00 | 4 d, 08 h | continuous | Track & Rail |  | LT | [8 empty] | Schienenerneuerung SE2 Weidenthal-Hochspeyer / ggf. SEV |  | N | 306477.02 | 2021-07-26 07:02 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 247AB055D47C8.01 | Saarbrücken Grenze - Ludwigshafen (Rhein) Überleitung Süd | < > | Weidenthal | Weidenthal | 2022 | 2022 | 8 | 13 | 2022-02-21 | 0:00 | 2022-03-28 23:59 | 23:59 | 36 d | continuous | Miscellaneous |  | ST | [8 empty] | Arbeiten am Bahnübergang Rückbau WP 90 (km 63,363) |  | N | 306208.01 | 2021-07-26 11:56 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 247D648888168.01 | Saarbrücken Grenze - Ludwigshafen (Rhein) Überleitung Süd | < > | Neustadt (Weinstr) Hbf | Neustadt (Weinstr) Hbf | 2022 | 2022 | 16 | 17 | 2022-04-18 07:00 | 7:00 | 2022-04-27 16:00 | 16:00 | 9 d, 09 h | continuous | Track & Rail |  | ST | [8 empty] | Schienenerneuerung SE2 Hochspeyer-Weidenthal |  | N | 306478.01 | 2021-07-28 08:32 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 247D648888168.03 | Saarbrücken Grenze - Ludwigshafen (Rhein) Überleitung Süd | > | Hochspeyer | Weidenthal | 2022 | 2022 | 16 | 17 | 2022-04-20 21:00 | 21:00 | 2022-04-25 05:00 | 5:00 | 4 d, 08 h | continuous | Track & Rail |  | LT | [8 empty] | Schienenerneuerung SE2 Hochspeyer-Weidenthal |  | N | 306478.03 | 2021-07-28 08:32 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 21E44BB4B4B8C.01 | Saarbrücken Grenze - Ludwigshafen (Rhein) Überleitung Süd | < > | Ludwigshafen (Rhein) Hbf tief | Ludwigshafen (Rhein) Hbf tief | 2022 | 2022 | 41 | 44 | 2022-10-10 | 0:00 | 2022-11-04 23:59 | 23:59 | 26 d | continuous | Track & Rail |  | ST | [8 empty] | Gleiserneuerung Gleis 3+4 |  | N | 306370.01 | 2020-04-27 07:19 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 21E44BB4B4B8C.02 | Saarbrücken Grenze - Ludwigshafen (Rhein) Überleitung Süd | < > | Neustadt (Weinstr) Ülp Ost | Neustadt (Weinstr) Ülp Ost | 2022 | 2022 | 41 | 44 | 2022-10-10 | 0:00 | 2022-11-04 23:59 | 23:59 | 26 d | continuous | Track & Rail |  | ST | [8 empty] | Gleiserneuerung Gleis 3+4 |  | N | 306370.02 | 2020-04-27 07:19 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 21E44BB4B4B8C.03 | Saarbrücken Grenze - Ludwigshafen (Rhein) Überleitung Süd | < > | Schifferstadt | Schifferstadt | 2022 | 2022 | 41 | 44 | 2022-10-10 | 0:00 | 2022-11-04 23:59 | 23:59 | 26 d | continuous | Track & Rail |  | ST | [8 empty] | Gleiserneuerung Gleis 3+4 |  | N | 306370.03 | 2020-04-27 07:19 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 22D93B4E267C8.03 | Saarbrücken Grenze - Ludwigshafen (Rhein) Überleitung Süd | < > | Saarbrücken Hbf | Saarbrücken Hbf | 2022 | 2022 | 41 | 42 | 2022-10-15 | 0:00 | 2022-10-17 05:30 | 5:30 | 2 d, 05 h | continuous | Switch |  | ST | [8 empty] | Weichenerneuerung Saarbrücken WE W 69+71 in Saarbrücken Hbf |  | N | 22D93B4E267C8.03 | 2020-10-29 09:39 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 21E44BB4B4B8C.05 | Saarbrücken Grenze - Ludwigshafen (Rhein) Überleitung Süd | < > | Schifferstadt | Schifferstadt | 2022 | 2022 | 41 | 44 | 2022-10-15 | 0:00 | 2022-10-31 04:30 | 4:30 | 16 d, 04 h | continuous | Track & Rail |  | ST | [8 empty] | Gleiserneuerung Gleis 3+4 |  | N | 306370.05 | 2020-04-27 07:19 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 21E44BC5652EC.01 | Saarbrücken Grenze - Ludwigshafen (Rhein) Überleitung Süd | < > | Schifferstadt | Schifferstadt | 2022 | 2022 | 41 | 44 | 2022-10-15 | 0:00 | 2022-10-31 04:30 | 4:30 | 16 d, 04 h | continuous | Track & Rail |  | ST | [8 empty] | Gleiserneuerung Gleis 3+4 |  | N | 306399.01 | 2020-04-27 07:19 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 21E44BC5652EC.03 | Saarbrücken Grenze - Ludwigshafen (Rhein) Überleitung Süd | < > | Schifferstadt | Schifferstadt | 2022 | 2022 | 42 | 43 | 2022-10-23 06:00 | 6:00 | 2022-10-30 22:00 | 22:00 | 1 d, 08 h | periodical | Track & Rail |  | ST | [8 empty] | Gleiserneuerung Gleis 3+4 |  | N | 306399.03 | 2020-04-27 07:19 |  | 7 | 1
DB Netz AG | 21E44BC5652EC.04 | Saarbrücken Grenze - Ludwigshafen (Rhein) Überleitung Süd | < | Ludwigshafen (Rhein) T51/52/53 | Schifferstadt | 2022 | 2022 | 42 | 43 | 2022-10-23 06:00 | 6:00 | 2022-10-30 22:00 | 22:00 | 1 d, 08 h | periodical | Track & Rail |  | LT | [8 empty] | Gleiserneuerung Gleis 3+4 |  | N | 306399.04 | 2020-04-27 07:19 |  | 7 | 1
DB Netz AG | 244A9B2C90028.03 | Homburg (Saar) Hbf - Saarbrücken Hbf | < > | Bexbach | Neunkirchen (Saar) Hbf | 2022 | 2022 | 4 | 4 | 2022-01-29 23:35 | 23:35 | 2022-01-30 07:45 | 7:45 | 8 h | continuous | Bridge | T | [9 empty] | Brückenarbeiten Ern EÜ Hilswiesen km 11,953 - Aufbau Gleismonitoring (Phase 1) / SEV |  | N | 106064.03 | 2021-06-23 10:56 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 2492018887C48.01 | Homburg (Saar) Hbf - Saarbrücken Hbf | < > | Homburg (Saar) Hbf | Homburg (Saar) Hbf | 2022 | 2022 | 12 | 13 | 2022-03-21 01:00 | 1:00 | 2022-03-28 03:00 | 3:00 | 7 d, 02 h | continuous | Track & Rail |  | ST | [8 empty] | Gleiserneuerung Gl.5008 in Homburg(Saar)Hbf |  | N | 106111.01 | 2021-08-11 12:30 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 2492018887C48.02 | Homburg (Saar) Hbf - Saarbrücken Hbf | < > | Homburg (Saar) Hbf | Homburg (Saar) Hbf | 2022 | 2022 | 12 | 13 | 2022-03-21 01:00 | 1:00 | 2022-03-28 03:00 | 3:00 | 7 d, 02 h | continuous | Track & Rail |  | ST | [8 empty] | Gleiserneuerung Gl.5008 in Homburg(Saar)Hbf |  | N | 106111.02 | 2021-08-11 12:30 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 24BDE777FAD28.01 | Homburg (Saar) Hbf - Saarbrücken Hbf | < > | Dudweiler | Dudweiler | 2022 | 2022 | 14 | 16 | 2022-04-04 07:00 | 7:00 | 2022-04-21 16:00 | 16:00 | 17 d, 09 h | continuous | Switch |  | ST | [8 empty] | Weichenerneuerung mit PSS Saarbrücken-Burbach W 501,583,584,587+W 531-535 |  | N | 306428.01 | 2021-09-10 16:30 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 24BDE777FAD28.02 | Homburg (Saar) Hbf - Saarbrücken Hbf | < > | Sulzbach (Saar) | Sulzbach (Saar) | 2022 | 2022 | 14 | 16 | 2022-04-04 07:00 | 7:00 | 2022-04-21 16:00 | 16:00 | 17 d, 09 h | continuous | Switch |  | ST | [8 empty] | Weichenerneuerung mit PSS Saarbrücken-Burbach W 501,583,584,587+W 531-535 |  | N | 306428.02 | 2021-09-10 16:30 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 21E44BA002DEC.01 | Homburg (Saar) Hbf - Saarbrücken Hbf | < > | Landsweiler-Reden | Landsweiler-Reden | 2022 | 2022 | 40 | 44 | 2022-10-07 | 0:00 | 2022-10-31 12:00 | 12:00 | 24 d, 12 h | continuous | Switch |  | ST | [8 empty] | Weichenerneuerung im Bf Wemmetsweiler |  | N | 306338.01 | 2020-04-27 07:18 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 21E44BA002DEC.02 | Homburg (Saar) Hbf - Saarbrücken Hbf | < > | Landsweiler-Reden | Landsweiler-Reden | 2022 | 2022 | 40 | 44 | 2022-10-07 | 0:00 | 2022-10-31 12:00 | 12:00 | 24 d, 12 h | continuous | Switch |  | ST | [8 empty] | Weichenerneuerung im Bf Wemmetsweiler |  | N | 306338.02 | 2020-04-27 07:18 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 21E44BA002DEC.03 | Homburg (Saar) Hbf - Saarbrücken Hbf | < > | Neunkirchen (Saar) Hbf | Neunkirchen (Saar) Hbf | 2022 | 2022 | 40 | 44 | 2022-10-07 | 0:00 | 2022-10-31 12:00 | 12:00 | 24 d, 12 h | continuous | Switch |  | ST | [8 empty] | Weichenerneuerung im Bf Wemmetsweiler |  | N | 306338.03 | 2020-04-27 07:18 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 21E446E24518C.01 | Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf | < > | Mannheim Rbf Gr D | Mannheim Rbf Gr D | 2022 | 2022 | 31 | 32 | 2022-08-03 | 0:00 | 2022-08-09 23:59 | 23:59 | 7 d | continuous | Track & Rail |  | ST | [8 empty] | Untergrundverbesserung 2022_3601_PSS RMF - RHBW |  | N | 306108.01 | 2021-07-06 18:34 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 21E44AC8DCBEC.01 | Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf | < > | Mannheim Rbf Gr D | Mannheim Rbf Gr D | 2022 | 2022 | 32 | 37 | 2022-08-10 | 0:00 | 2022-09-14 23:59 | 23:59 | 36 d | continuous | Track & Rail |  | ST | [8 empty] | Gleiserneuerung mit BR und PSS 22_MA-Edingen - HD-Wieblingen |  | N | 306999.01 | 2020-07-15 10:20 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 21E44AC8DCBEC.02 | Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf | < > | Mannheim Rbf Gr K/Kn | Mannheim Rbf Gr K/Kn | 2022 | 2022 | 32 | 37 | 2022-08-10 | 0:00 | 2022-09-14 23:59 | 23:59 | 36 d | continuous | Track & Rail |  | ST | [8 empty] | Gleiserneuerung mit BR und PSS 22_MA-Edingen - HD-Wieblingen |  | N | 306999.02 | 2020-07-15 10:20 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 22D92A58EF206.01 | Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf | < > | Mannheim-Friedrichsfeld Südeinf/Ausf | Mannheim Rbf Gr K/Kn | 2022 | 2022 | 33 | 33 | 2022-08-15 22:00 | 22:00 | 2022-08-19 05:00 | 5:00 | 1 d, 04 h | periodical | Track & Rail | T | [9 empty] | Gleiserneuerung mit BR und PSS RMF-RHBW (Str 4000) - Erg zu J(XEI) |  | N | 22D92A58EF206.01 | 2020-10-12 13:52 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 22D92A58EF206.02 | Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf | < > | Mannheim-Friedrichsfeld Südeinf/Ausf | Mannheim Rbf Gr K/Kn | 2022 | 2022 | 33 | 34 | 2022-08-19 22:00 | 22:00 | 2022-08-22 05:00 | 5:00 | 2 d, 07 h | continuous | Track & Rail | T | [9 empty] | Gleiserneuerung mit BR und PSS RMF-RHBW (Str 4000) - Erg zu J(XEI) |  | N | 22D92A58EF206.02 | 2020-10-12 13:52 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 22D92AF33D146.01 | Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf | < > | Mannheim-Friedrichsfeld Südeinf/Ausf | Mannheim Rbf Gr K/Kn | 2022 | 2022 | 34 | 36 | 2022-08-22 22:00 | 22:00 | 2022-09-09 05:00 | 5:00 | 5 d, 06 h | periodical | Track & Rail | T | [9 empty] | Gleiserneuerung mit BR und PSS RMF-RHBW (Str 4000) - Erg zu J(XEI) |  | N | 22D92AF33D146.01 | 2020-10-12 13:54 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 22D948B7AB286.04 | Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf | < > | Mannheim-Friedrichsfeld Südeinf/Ausf | Mannheim Rbf Gr K/Kn | 2022 | 2022 | 47 | 47 | 2022-11-26 21:40 | 21:40 | 2022-11-27 04:10 | 4:10 | 6 h | continuous | Track & Rail | T | [9 empty] | Gleiserneuerung mit BR und PSS RMF-RHBW (Str 4000) - B-Stopfgang (Bereich RMFE) / SEV |  | N | 206428.04 | 2020-12-14 15:32 |  | 1,2,3,4,5,6,7 | 1
DB Netz AG | 22D94937A6D46.04 | Mannheim Hbf - Mannheim-Friedrichsfeld Südeinf/Ausf | < > | Mannheim-Friedrichsfeld Südeinf/Ausf | Mannheim Rbf Gr K/Kn | 2022 | 2022 | 47 | 48 | 2022-11-27 21:40 | 21:40 | 2022-11-28 04:10 | 4:10 | 6 h | continuous | Track & Rail | T | [9 empty] | Gleiserneuerung mit BR und PSS RMF-RHBW (Str 4000) - B-Stopfgang (Bereich RMFE) / SEV |  | N | 206429.04 | 2020-12-14 15:47 |  | 1,2,3,4,5,6,7 | 1
Infraestruturas de Portugal S.A. | 0094-Z.A_04_00 |  | < > | Nine | Braga | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:30 | 2024-12-31 | 4:30 | 4h | Periodical | Maintenance | [5 empty] | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_05_00 |  | < > | Contumil | Leixões | 2022 | 2024 | 1 | 53 | 2022-01-01 | 4:00 | 2024-12-31 | 8:00 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_06_00-0 |  | < > | Ermesinde | Caíde | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:30 | 2024-12-31 | 4:30 | 4h | Periodical | Maintenance | [5 empty] | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_06_00-1 |  | < > | Caíde | Pocinho | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:30 | 2024-12-31 | 4:30 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_08_00 |  | < > | Lisboa Santa Apolónia | Azambuja | 2022 | 2024 | 1 | 53 | 2022-01-01 | 1:00 | 2024-12-31 | 5:00 | 4h | Periodical | Maintenance | [5 empty] | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_08_02 |  | < > | Azambuja | Alfarelos | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:30 | 2024-12-31 | 4:30 | 4h | Periodical | Maintenance | [5 empty] | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_08_04 |  | < > | Alfarelos | Porto Campanhã | 2022 | 2024 | 1 | 53 | 2022-01-01 | 1:00 | 2024-12-31 | 5:00 | 4h | Periodical | Maintenance | [5 empty] | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_09_00 |  | < > | Lousado | Guimarães | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:40 | 2024-12-31 | 4:40 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_20_00 |  | < > | Pampilhosa | Bifurcação do Luso | 2022 | 2024 | 1 | 53 | 2022-01-01 | 4:45 | 2024-12-31 | 8:45 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_20_02 |  | < > | Bifurcação do Luso | Mortágua | 2022 | 2024 | 1 | 53 | 2022-01-01 | 4:35 | 2024-12-31 | 8:35 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_20_04 |  | < > | Mortágua | Carregal do Sal | 2022 | 2024 | 1 | 53 | 2022-01-01 | 4:10 | 2024-12-31 | 8:10 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_20_06 |  | < > | Carregal do Sal | Nelas | 2022 | 2024 | 1 | 53 | 2022-01-01 | 3:50 | 2024-12-31 | 7:50 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_20_08 |  | < > | Nelas | Contenças | 2022 | 2024 | 1 | 53 | 2022-01-01 | 3:40 | 2024-12-31 | 7:40 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_20_10 |  | < > | Contenças | Fornos de Algodres | 2022 | 2024 | 1 | 53 | 2022-01-01 | 3:25 | 2024-12-31 | 7:25 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_20_12 |  | < > | Fornos de Algodres | Celorico da Beira | 2022 | 2024 | 1 | 53 | 2022-01-01 | 3:10 | 2024-12-31 | 7:10 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_20_14 |  | < > | Celorico da Beira | Guarda | 2022 | 2024 | 1 | 53 | 2022-01-01 | 2:55 | 2024-12-31 | 6:55 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_20_16 |  | < > | Guarda | Vilar Formoso Fronteira | 2022 | 2024 | 1 | 53 | 2022-01-01 | 2:55 | 2024-12-31 | 6:55 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_21_00 |  | < > | Coimbra B | Coimbra | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:30 | 2024-12-31 | 4:30 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_22_00 |  | < > | Bifurcação de Lares | Alfarelos | 2022 | 2024 | 1 | 53 | 2022-01-01 | 1:40 | 2024-12-31 | 5:40 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_23_00 |  | < > | Agualva-Cacém | Louriçal | 2022 | 2024 | 1 | 53 | 2022-01-01 | 1:40 | 2024-12-31 | 5:40 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_23_02 |  | < > | Louriçal | Amieira | 2022 | 2024 | 1 | 53 | 2022-01-01 | 1:50 | 2024-12-31 | 5:50 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_23_04 |  | < > | Amieira | Figueira da Foz | 2022 | 2024 | 1 | 53 | 2022-01-01 | 1:40 | 2024-12-31 | 5:40 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_24_00 |  | < > | Lamarosa | Tomar | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:50 | 2024-12-31 | 4:50 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_25_00 |  | < > | Entroncamento | Ródão | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:20 | 2024-12-31 | 4:20 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_25_02 |  | < > | Ródão | Sarnadas | 2022 | 2024 | 1 | 53 | 2022-01-01 | 4:50 | 2024-12-31 | 8:50 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_25_04 |  | < > | Sarnadas | Castelo Branco | 2022 | 2024 | 1 | 53 | 2022-01-01 | 4:35 | 2024-12-31 | 8:35 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_25_06 |  | < > | Castelo Branco | Lardosa | 2022 | 2024 | 1 | 53 | 2022-01-01 | 4:20 | 2024-12-31 | 8:20 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_25_08 |  | < > | Lardosa | Vale de Prazeres | 2022 | 2024 | 1 | 53 | 2022-01-01 | 4:10 | 2024-12-31 | 8:10 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_25_10 |  | < > | Vale de Prazeres | Fundão | 2022 | 2024 | 1 | 53 | 2022-01-01 | 4:00 | 2024-12-31 | 8:00 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_25_12 |  | < > | Fundão | Covilhã | 2022 | 2024 | 1 | 53 | 2022-01-01 | 3:50 | 2024-12-31 | 7:50 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_25_14 |  | < > | Covilhã | Belmonte-Manteigas | 2022 | 2024 | 1 | 53 | 2022-01-01 | 3:50 | 2024-12-31 | 7:50 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_25_16 |  | < > | Belmonte-Manteigas | Guarda | 2022 | 2024 | 1 | 53 | 2022-01-01 | 3:30 | 2024-12-31 | 7:30 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_27_00 |  | < > | Abrantes | Elvas Fronteira | 2022 | 2024 | 1 | 53 | 2022-01-01 | 3:15 | 2024-12-31 | 7:15 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_28_00 |  | < > | Lisboa Rossio | Sintra | 2022 | 2024 | 1 | 53 | 2022-01-01 | 1:00 | 2024-12-31 | 5:00 | 4h | Periodical | Maintenance | [5 empty] | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_29_00 |  | < > | Alcântara-Terra | Campolide-A | 2022 | 2024 | 1 | 53 | 2022-01-01 | 1:15 | 2024-12-31 | 5:15 | 4h | Periodical | Maintenance | [5 empty] | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_29_02 |  | < > | Campolide-A | Braço de Prata | 2022 | 2024 | 1 | 53 | 2022-01-01 | 1:00 | 2024-12-31 | 5:00 | 4h | Periodical | Maintenance | [5 empty] | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_32_00 |  | < > | Cais do Sodré | Cascais | 2022 | 2024 | 1 | 53 | 2022-01-01 | 1:45 | 2024-12-31 | 5:45 | 4h | Periodical | Maintenance | [5 empty] | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_33_00 |  | < > | Setil | Vendas Novas | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:30 | 2024-12-31 | 4:30 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_34_00 |  | < > | Barreiro | Pinhal Novo | 2022 | 2024 | 1 | 53 | 2022-01-01 | 1:00 | 2024-12-31 | 5:00 | 4h | Periodical | Maintenance | [5 empty] | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_34_02-1 |  | < > | Pinhal Novo | Poceirão | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:30 | 2024-12-31 | 4:30 | 4h | Periodical | Maintenance | [5 empty] | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_34_02-0 |  | < > | Poceirão | Beja | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:30 | 2024-12-31 | 4:30 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_34_04 |  | < > | Ourique | Funcheira | 2022 | 2024 | 1 | 53 | 2022-01-01 | 20:30 | 2024-12-31 | 24:30 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_37_00 |  | < > | Campolide-A | Pragal | 2022 | 2024 | 1 | 53 | 2022-01-01 | 1:15 | 2024-12-31 | 5:15 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_37_02 |  | < > | Pragal | Setúbal | 2022 | 2024 | 1 | 53 | 2022-01-01 | 1:00 | 2024-12-31 | 5:00 | 4h | Periodical | Maintenance | [5 empty] | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_37_04 |  | < > | Setúbal | Bifurcação de Águas de Moura - Sul | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:10 | 2024-12-31 | 4:10 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_37_06 |  | < > | Bifurcação de Águas de Moura - Sul | Bifurcação de Ermidas - Sul | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:10 | 2024-12-31 | 4:30 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_37_08 |  | < > | Bifurcação de Ermidas - Sul | Funcheira | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:30 | 2024-12-31 | 5:00 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_37_10 |  | < > | Funcheira | Luzianes | 2022 | 2024 | 1 | 53 | 2022-01-01 | 1:00 | 2024-12-31 | 5:30 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_37_12 |  | < > | Luzianes | São Marcos | 2022 | 2024 | 1 | 53 | 2022-01-01 | 1:30 | 2024-12-31 | 6:00 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_37_14 |  | < > | São Marcos | Tunes | 2022 | 2024 | 1 | 53 | 2022-01-01 | 2:00 | 2024-12-31 | 6:00 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_38_00 |  | < > | Ermidas - Sado | Porto de Sines | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:00 | 2024-12-31 | 4:00 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_39_00 |  | < > | Casa Branca | Évora | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:30 | 2024-12-31 | 4:30 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_45_00 |  | < > | Lagos | Tunes | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:00 | 2024-12-31 | 4:00 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_45_02 |  | < > | Tunes | Faro | 2022 | 2024 | 1 | 53 | 2022-01-01 | 2:00 | 2024-12-31 | 6:00 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_45_04 |  | < > | Faro | Vila Real de Stº António | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:00 | 2024-12-31 | 4:00 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_46_00 |  | < > | Bifurcação do Poceirão - Descendente | Bifurcação de Águas de Moura - Sul | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:30 | 2024-12-31 | 4:30 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-11-11 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_48_00 |  | < > | Bifurcação da Funcheira - Sul | Bifurcação da Funcheira - Alentejo | 2022 | 2024 | 1 | 53 | 2022-01-01 | 20:30 | 2024-12-31 | 24:30 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-12-23 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_49_00 |  | < > | Bifurcação de Ermidas - Sines | Bifurcação de Ermidas - Sul | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:00 | 2024-12-31 | 4:00 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-12-23 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_52_00 |  | < > | Amieira | Bifurcação de Verride | 2022 | 2024 | 1 | 53 | 2022-01-01 | 1:40 | 2024-12-31 | 5:40 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-12-23 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_53_00 |  | < > | Poceirão | Bifurcação de Agualva | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:30 | 2024-12-31 | 4:30 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-12-23 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_54_00 |  | < > | Águas de Moura | Bifurcação de Águas de Moura - Norte | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:30 | 2024-12-31 | 4:30 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-12-23 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_55_00 |  | < > | Vidigal | Bombel | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:30 | 2024-12-31 | 4:30 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-12-23 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_56_00 |  | < > | Bifurcação de Chelas | Bifurcação de Xabregas | 2022 | 2024 | 1 | 53 | 2022-01-01 | 1:00 | 2024-12-31 | 5:00 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-12-23 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_57_00 |  | < > | Sete Rios | Benfica | 2022 | 2024 | 1 | 53 | 2022-01-01 | 1:00 | 2024-12-31 | 5:00 | 4h | Periodical | Maintenance | [5 empty] | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-12-23 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_58_00 |  | < > | Louriçal | Ramal Celbi/Ramal Soporcel (Inserção) | 2022 | 2024 | 1 | 53 | 2022-01-01 | 1:50 | 2024-12-31 | 5:50 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-12-23 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_63_00 |  | < > | Lisboa Santa Apolónia | Ramal da Sotagus (Inserção lado Matinha) | 2022 | 2024 | 1 | 53 | 2022-01-01 | 1:50 | 2024-12-31 | 5:50 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-12-23 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_68_00 |  | < > | Pinheiro | Grândola Norte | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:10 | 2024-12-31 | 4:10 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-12-23 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_69_00 |  | < > | Bifurcação Norte do Setil | Bifurcação do Setil - Vendas Novas | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:30 | 2024-12-31 | 4:30 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-12-23 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_186_00 |  | < > | Bifurcação das Beiras - Beira Baixa | Bifurcação das Beiras - Beira Alta | 2022 | 2024 | 1 | 53 | 2022-01-01 | 3:20 | 2024-12-31 | 7:20 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-12-23 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_79_00 |  | < > | Ourique | Minas de Neves Corvo | 2022 | 2024 | 1 | 53 | 2022-01-01 | 20:30 | 2024-12-31 | 24:30 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-12-23 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_82_00 |  | < > | Coina | Ramal da Siderurgia Nacional (Inserção) | 2022 | 2024 | 1 | 53 | 2022-01-01 | 1:00 | 2024-12-31 | 5:00 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-12-23 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-Z.A_90_00 |  | < > | Complexo de Coina | Triagem Porto de Aveiro | 2022 | 2024 | 1 | 53 | 2022-01-01 | 0:30 | 2024-12-31 | 4:30 | 4h | Periodical | Maintenance | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Zonas Azuis |  | Y |  | 2021-12-23 | Minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Planned | N
Infraestruturas de Portugal S.A. | 0094-REN_25_01 |  | < > | Barquinha | Mouriscas | 2024 | 2024 | 1 | 40 | 2024-01-01 | 0:20 | 2024-09-30 | 5:20 | 5h | Periodical | Miscellaneous | T | [5 empty] | ,, | ,, | ,, |  | Estabilização de Taludes de escavação e aterro |  |  |  | 2021-12-23 | Medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_05_00 |  | < > | Leixões | Leixões | 2023 | 2025 | 13 | 27 | 2023-04-01 | 2:00 | 2025-06-30 | 8:00 | 6h | Periodical | Track & Rail | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Construção de linhas de resguardo e alteração do Layout de Leixões |  |  |  | 2021-12-23 | Medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_08_03-1 |  | < > | Alfarelos | Pampilhosa | 2023 | 2023 | 1 | 40 | 2023-01-01 | 1:00 | 2023-10-01 | 5:30 | 5,5h | Periodical | Miscellaneous |  | LT+ST | S |  |  | ,, | ,, | ,, | ,, |  | Alteração do layout da estação de Alfarelos e Passagens Desniveladas |  |  |  | 2021-12-23 | Medium | 1,2,3,4,5 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_08_03-0 |  | < > | Alfarelos | Pampilhosa | 2023 | 2023 | 1 | 40 | 2023-01-01 | 23:00 | 2023-10-01 | 6:00 | 7h | Periodical | Miscellaneous |  | LT+ST | S |  |  | ,, | ,, | ,, | ,, |  | Alteração do layout da estação de Alfarelos e Passagens Desniveladas |  |  |  | 2021-12-23 | Medium | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_08_06-0 |  | < > | Válega | Granja | 2022 | 2023 | 28 | 53 | 2022-07-04 | 23:00 | 2023-12-31 | 5:00 | 6h | Periodical | Miscellaneous |  | LT+ST |  |  |  | ,, | ,, | ,, | ,, |  | RIV no troço Ovar / Espinho |  |  |  | 2021-12-23 | Medium | 1,2,3,4,5 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_08_06-1 |  | < > | Válega | Granja | 2022 | 2023 | 28 | 53 | 2022-07-04 | 22:00 | 2023-12-31 | 0:00 | 2h | Periodical | Miscellaneous |  | LT+ST |  |  |  | ,, | ,, | ,, | ,, |  | RIV no troço Ovar / Espinho |  |  |  | 2021-12-23 | Medium | 7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_08_06-2 |  | < > | Válega | Granja | 2022 | 2023 | 28 | 53 | 2022-07-04 | 0:00 | 2023-12-31 | 5:00 | 5h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | RIV no troço Ovar / Espinho |  |  |  | 2021-12-23 | Medium | 1 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_08_06-3 |  | < > | Válega | Granja | 2022 | 2023 | 28 | 53 | 2022-07-04 | 5:00 | 2023-12-31 | 7:00 | 2h | Periodical | Miscellaneous |  | LT+ST |  |  |  | ,, | ,, | ,, | ,, |  | RIV no troço Ovar / Espinho |  |  |  | 2021-12-23 | Medium | 1 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_08_06-4 |  | < > | Válega | Granja | 2022 | 2023 | 28 | 53 | 2022-07-04 | 22:00 | 2023-12-31 | 0:00 | 2h | Periodical | Miscellaneous |  | LT+ST |  |  |  | ,, | ,, | ,, | ,, |  | RIV no troço Ovar / Espinho |  |  |  | 2021-12-23 | Medium | 7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_08_06-5 |  | < > | Válega | Granja | 2022 | 2023 | 28 | 53 | 2022-07-04 | 0:00 | 2023-12-31 | 8:00 | 8h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | RIV no troço Ovar / Espinho |  |  |  | 2021-12-23 | Medium | 7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_08_06-6 |  | < > | Válega | Granja | 2022 | 2023 | 28 | 53 | 2022-07-04 | 8:00 | 2023-12-31 | 10:00 | 2h | Periodical | Miscellaneous |  | LT+ST |  |  |  | ,, | ,, | ,, | ,, |  | RIV no troço Ovar / Espinho |  |  |  | 2021-12-23 | Medium | 7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_08_11-1 |  | < > | Esmoriz | Campanhã | 2020 | 2022 | 27 | 28 | 2020-07-04 | 23:00 | 2022-07-03 | 5:00 | 6h | Periodical | Miscellaneous |  | LT+ST |  |  |  | ,, | ,, | ,, | ,, |  | RIV no troço Ovar / Espinho |  |  |  | 2021-12-23 | Medium | 1,2,3,4,5 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_08_11-2 |  | < > | Esmoriz | Campanhã | 2020 | 2022 | 27 | 28 | 2020-07-04 | 22:00 | 2022-07-03 | 0:00 | 2h | Periodical | Miscellaneous |  | LT+ST |  |  |  | ,, | ,, | ,, | ,, |  | RIV no troço Ovar / Espinho |  |  |  | 2021-12-23 | Medium | 7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_08_11-3 |  | < > | Esmoriz | Campanhã | 2020 | 2022 | 27 | 28 | 2020-07-04 | 0:00 | 2022-07-03 | 5:00 | 5h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | RIV no troço Ovar / Espinho |  |  |  | 2021-12-23 | Medium | 1 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_08_11-4 |  | < > | Esmoriz | Campanhã | 2020 | 2022 | 27 | 28 | 2020-07-04 | 5:00 | 2022-07-03 | 7:00 | 2h | Periodical | Miscellaneous |  | LT+ST |  |  |  | ,, | ,, | ,, | ,, |  | RIV no troço Ovar / Espinho |  |  |  | 2021-12-23 | Medium | 1 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_08_11-5 |  | < > | Esmoriz | Campanhã | 2020 | 2022 | 27 | 28 | 2020-07-04 | 22:00 | 2022-07-03 | 0:00 | 2h | Periodical | Miscellaneous |  | LT+ST |  |  |  | ,, | ,, | ,, | ,, |  | RIV no troço Ovar / Espinho |  |  |  | 2021-12-23 | Medium | 7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_08_11-6 |  | < > | Esmoriz | Campanhã | 2020 | 2022 | 27 | 28 | 2020-07-04 | 0:00 | 2022-07-03 | 8:00 | 8h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | RIV no troço Ovar / Espinho |  |  |  | 2021-12-23 | Medium | 7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_08_11-0 |  | < > | Esmoriz | Campanhã | 2020 | 2022 | 27 | 28 | 2020-07-04 | 8:00 | 2022-07-03 | 10:00 | 2h | Periodical | Miscellaneous |  | LT+ST |  |  |  | ,, | ,, | ,, | ,, |  | RIV no troço Ovar / Espinho |  |  |  | 2021-12-23 | Medium | 7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_20_07-1 |  | < > | Cerdeira | Vilar Formoso | 2021 | 2023 | 15 | 53 | 2021-04-05 | 0:30 | 2023-12-31 | 8:30 | 8h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Beira Alta |  |  |  | 2021-12-23 | Medium | 1,2,3,4,5 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_20_07-0 |  | < > | Cerdeira | Vilar Formoso | 2021 | 2023 | 15 | 53 | 2021-04-05 | 22:30 | 2023-12-31 | 11:30 | 13h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Beira Alta |  |  |  | 2021-12-23 | Medium | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_02-2 |  | < > | Ermidas - Sado | Raquete | 2021 | 2023 | 41 | 53 | 2021-10-04 | 0:00 | 2023-12-31 | 8:00 | 8h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha de Sines e sinalização |  |  |  | 2021-12-23 | Medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_02-1.0 |  | < > | Ermidas - Sado | Raquete | 2022 | 2022 | 7 | 8 | 2022-02-07 | 0:00 | 2022-02-13 | 12:00 | 12h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha de Sines e sinalização |  |  |  | 2021-12-23 | Medium | 7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_02-1.1 |  | < > | Ermidas - Sado | Raquete | 2022 | 2022 | 15 | 16 | 2022-04-04 | 0:00 | 2022-04-10 | 12:00 | 12h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha de Sines e sinalização |  |  |  | 2021-12-23 | Medium | 7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_02-1.2 |  | < > | Ermidas - Sado | Raquete | 2022 | 2022 | 23 | 24 | 2022-05-30 | 0:00 | 2022-06-05 | 12:00 | 12h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha de Sines e sinalização |  |  |  | 2021-12-23 | Medium | 7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_02-1.3 |  | < > | Ermidas - Sado | Raquete | 2022 | 2022 | 31 | 32 | 2022-07-25 | 0:00 | 2022-07-31 | 12:00 | 12h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha de Sines e sinalização |  |  |  | 2021-12-23 | Medium | 7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_02-1.4 |  | < > | Ermidas - Sado | Raquete | 2022 | 2022 | 39 | 40 | 2022-09-19 | 0:00 | 2022-09-25 | 12:00 | 12h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha de Sines e sinalização |  |  |  | 2021-12-23 | Medium | 7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_02-1.5 |  | < > | Ermidas - Sado | Raquete | 2022 | 2022 | 47 | 48 | 2022-11-14 | 0:00 | 2022-11-20 | 12:00 | 12h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha de Sines e sinalização |  |  |  | 2021-12-23 | Medium | 7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_02-1.6 |  | < > | Ermidas - Sado | Raquete | 2023 | 2023 | 2 | 3 | 2023-01-09 | 0:00 | 2023-01-15 | 12:00 | 12h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha de Sines e sinalização |  |  |  | 2021-12-23 | Medium | 7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_02-1.7 |  | < > | Ermidas - Sado | Raquete | 2023 | 2023 | 10 | 11 | 2023-03-06 | 0:00 | 2023-03-12 | 12:00 | 12h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha de Sines e sinalização |  |  |  | 2021-12-23 | Medium | 7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_02-1.8 |  | < > | Ermidas - Sado | Raquete | 2023 | 2023 | 18 | 19 | 2023-05-01 | 0:00 | 2023-05-07 | 12:00 | 12h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha de Sines e sinalização |  |  |  | 2021-12-23 | Medium | 7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_02-1.9 |  | < > | Ermidas - Sado | Raquete | 2023 | 2023 | 26 | 27 | 2023-06-26 | 0:00 | 2023-07-02 | 12:00 | 12h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha de Sines e sinalização |  |  |  | 2021-12-23 | Medium | 7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_02-1.10 |  | < > | Ermidas - Sado | Raquete | 2023 | 2023 | 34 | 35 | 2023-08-21 | 0:00 | 2023-08-27 | 12:00 | 12h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha de Sines e sinalização |  |  |  | 2021-12-23 | Medium | 7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_02-1.11 |  | < > | Ermidas - Sado | Raquete | 2023 | 2023 | 42 | 43 | 2023-10-16 | 0:00 | 2023-10-22 | 12:00 | 12h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha de Sines e sinalização |  |  |  | 2021-12-23 | Medium | 7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_02-0.0 |  | < > | Ermidas - Sado | Raquete | 2022 | 2022 | 3 | 4 | 2022-01-10 | 0:00 | 2022-01-16 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha de Sines e sinalização |  |  |  | 2021-12-23 | Medium | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_02-0.1 |  | < > | Ermidas - Sado | Raquete | 2022 | 2022 | 11 | 12 | 2022-03-07 | 0:00 | 2022-03-13 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha de Sines e sinalização |  |  |  | 2021-12-23 | Medium | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_02-0.2 |  | < > | Ermidas - Sado | Raquete | 2022 | 2022 | 19 | 20 | 2022-05-02 | 0:00 | 2022-05-08 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha de Sines e sinalização |  |  |  | 2021-12-23 | Medium | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_02-0.3 |  | < > | Ermidas - Sado | Raquete | 2022 | 2022 | 27 | 28 | 2022-06-27 | 0:00 | 2022-07-03 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha de Sines e sinalização |  |  |  | 2021-12-23 | Medium | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_02-0.4 |  | < > | Ermidas - Sado | Raquete | 2022 | 2022 | 35 | 36 | 2022-08-22 | 0:00 | 2022-08-28 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha de Sines e sinalização |  |  |  | 2021-12-23 | Medium | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_02-0.5 |  | < > | Ermidas - Sado | Raquete | 2022 | 2022 | 43 | 44 | 2022-10-17 | 0:00 | 2022-10-23 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha de Sines e sinalização |  |  |  | 2021-12-23 | Medium | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_02-0.6 |  | < > | Ermidas - Sado | Raquete | 2022 | 2022 | 51 | 52 | 2022-12-12 | 0:00 | 2022-12-18 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha de Sines e sinalização |  |  |  | 2021-12-23 | Medium | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_02-0.7 |  | < > | Ermidas - Sado | Raquete | 2023 | 2023 | 6 | 7 | 2023-02-06 | 0:00 | 2023-02-12 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha de Sines e sinalização |  |  |  | 2021-12-23 | Medium | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_02-0.8 |  | < > | Ermidas - Sado | Raquete | 2023 | 2023 | 14 | 15 | 2023-04-03 | 0:00 | 2023-04-09 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha de Sines e sinalização |  |  |  | 2021-12-23 | Medium | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_02-0.9 |  | < > | Ermidas - Sado | Raquete | 2023 | 2023 | 22 | 23 | 2023-05-29 | 0:00 | 2023-06-04 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha de Sines e sinalização |  |  |  | 2021-12-23 | Medium | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_02-0.10 |  | < > | Ermidas - Sado | Raquete | 2023 | 2023 | 30 | 31 | 2023-07-24 | 0:00 | 2023-07-30 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha de Sines e sinalização |  |  |  | 2021-12-23 | Medium | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_02-0.11 |  | < > | Ermidas - Sado | Raquete | 2023 | 2023 | 38 | 39 | 2023-09-18 | 0:00 | 2023-09-24 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha de Sines e sinalização |  |  |  | 2021-12-23 | Medium | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-3 |  | < > | Setil | Vendas Novas | 2022 | 2025 | 15 | 27 | 2022-04-04 | 0:00 | 2025-07-03 | 8:00 | 8h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 1,2,3,4,5,6 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_33_03-2 |  | < > | Setil | Vendas Novas | 2022 | 2025 | 15 | 27 | 2022-04-04 | 0:00 | 2025-07-03 | 12:00 | 12h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-1.0 |  | < > | Setil | Vendas Novas | 2022 | 2022 | 16 | 17 | 2022-04-11 | 0:00 | 2022-04-17 | 0:00 | 24h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-1.1 |  | < > | Setil | Vendas Novas | 2022 | 2022 | 40 | 41 | 2022-09-26 | 0:00 | 2022-10-02 | 0:00 | 24h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-1.2 |  | < > | Setil | Vendas Novas | 2023 | 2023 | 11 | 12 | 2023-03-13 | 0:00 | 2023-03-19 | 0:00 | 24h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-1.3 |  | < > | Setil | Vendas Novas | 2023 | 2023 | 35 | 36 | 2023-08-28 | 0:00 | 2023-09-03 | 0:00 | 24h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-1.4 |  | < > | Setil | Vendas Novas | 2024 | 2024 | 7 | 8 | 2024-02-12 | 0:00 | 2024-02-18 | 0:00 | 24h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-1.5 |  | < > | Setil | Vendas Novas | 2024 | 2024 | 31 | 32 | 2024-07-29 | 0:00 | 2024-08-04 | 0:00 | 24h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-1.6 |  | < > | Setil | Vendas Novas | 2025 | 2025 | 3 | 4 | 2025-01-13 | 0:00 | 2025-01-19 | 0:00 | 24h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.0 |  | < > | Setil | Vendas Novas | 2022 | 2022 | 15 | 16 | 2022-04-04 | 0:00 | 2022-04-10 | 0:00 | 48h | Periodical | Miscellaneous | T | LT+ST | S |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.1 |  | < > | Setil | Vendas Novas | 2022 | 2022 | 18 | 19 | 2022-04-25 | 0:00 | 2022-05-01 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.2 |  | < > | Setil | Vendas Novas | 2022 | 2022 | 21 | 22 | 2022-05-16 | 0:00 | 2022-05-22 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0. |  | < > | Setil | Vendas Novas | 2022 | 2022 | 24 | 25 | 2022-06-06 | 0:00 | 2022-06-12 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.3 |  | < > | Setil | Vendas Novas | 2022 | 2022 | 27 | 28 | 2022-06-27 | 0:00 | 2022-07-03 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.4 |  | < > | Setil | Vendas Novas | 2022 | 2022 | 30 | 31 | 2022-07-18 | 0:00 | 2022-07-24 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.5 |  | < > | Setil | Vendas Novas | 2022 | 2022 | 33 | 34 | 2022-08-08 | 0:00 | 2022-08-14 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.6 |  | < > | Setil | Vendas Novas | 2022 | 2022 | 36 | 37 | 2022-08-29 | 0:00 | 2022-09-04 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.7 |  | < > | Setil | Vendas Novas | 2022 | 2022 | 39 | 40 | 2022-09-19 | 0:00 | 2022-09-25 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.8 |  | < > | Setil | Vendas Novas | 2022 | 2022 | 42 | 43 | 2022-10-10 | 0:00 | 2022-10-16 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.9 |  | < > | Setil | Vendas Novas | 2022 | 2022 | 45 | 46 | 2022-10-31 | 0:00 | 2022-11-06 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.10 |  | < > | Setil | Vendas Novas | 2022 | 2022 | 48 | 49 | 2022-11-21 | 0:00 | 2022-11-27 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.11 |  | < > | Setil | Vendas Novas | 2022 | 2022 | 51 | 52 | 2022-12-12 | 0:00 | 2022-12-18 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.12 |  | < > | Setil | Vendas Novas | 2023 | 2023 | 1 | 2 | 2023-01-02 | 0:00 | 2023-01-08 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.13 |  | < > | Setil | Vendas Novas | 2023 | 2023 | 4 | 5 | 2023-01-23 | 0:00 | 2023-01-29 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.14 |  | < > | Setil | Vendas Novas | 2023 | 2023 | 7 | 8 | 2023-02-13 | 0:00 | 2023-02-19 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.15 |  | < > | Setil | Vendas Novas | 2023 | 2023 | 10 | 11 | 2023-03-06 | 0:00 | 2023-03-12 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.16 |  | < > | Setil | Vendas Novas | 2023 | 2023 | 13 | 14 | 2023-03-27 | 0:00 | 2023-04-02 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.17 |  | < > | Setil | Vendas Novas | 2023 | 2023 | 16 | 17 | 2023-04-17 | 0:00 | 2023-04-23 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.18 |  | < > | Setil | Vendas Novas | 2023 | 2023 | 19 | 20 | 2023-05-08 | 0:00 | 2023-05-14 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.19 |  | < > | Setil | Vendas Novas | 2023 | 2023 | 22 | 23 | 2023-05-29 | 0:00 | 2023-06-04 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.20 |  | < > | Setil | Vendas Novas | 2023 | 2023 | 25 | 26 | 2023-06-19 | 0:00 | 2023-06-25 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.21 |  | < > | Setil | Vendas Novas | 2023 | 2023 | 28 | 29 | 2023-07-10 | 0:00 | 2023-07-16 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.22 |  | < > | Setil | Vendas Novas | 2023 | 2023 | 31 | 32 | 2023-07-31 | 0:00 | 2023-08-06 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.23 |  | < > | Setil | Vendas Novas | 2023 | 2023 | 34 | 35 | 2023-08-21 | 0:00 | 2023-08-27 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.24 |  | < > | Setil | Vendas Novas | 2023 | 2023 | 37 | 38 | 2023-09-11 | 0:00 | 2023-09-17 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.25 |  | < > | Setil | Vendas Novas | 2023 | 2023 | 40 | 41 | 2023-10-02 | 0:00 | 2023-10-08 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.26 |  | < > | Setil | Vendas Novas | 2023 | 2023 | 43 | 44 | 2023-10-23 | 0:00 | 2023-10-29 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.27 |  | < > | Setil | Vendas Novas | 2023 | 2023 | 46 | 47 | 2023-11-13 | 0:00 | 2023-11-19 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.28 |  | < > | Setil | Vendas Novas | 2023 | 2023 | 49 | 50 | 2023-12-04 | 0:00 | 2023-12-10 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.29 |  | < > | Setil | Vendas Novas | 2023 | 2023 | 52 | 53 | 2023-12-25 | 0:00 | 2023-12-31 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.30 |  | < > | Setil | Vendas Novas | 2024 | 2024 | 3 | 4 | 2024-01-15 | 0:00 | 2024-01-21 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.31 |  | < > | Setil | Vendas Novas | 2024 | 2024 | 6 | 7 | 2024-02-05 | 0:00 | 2024-02-11 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.32 |  | < > | Setil | Vendas Novas | 2024 | 2024 | 9 | 10 | 2024-02-26 | 0:00 | 2024-03-03 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.33 |  | < > | Setil | Vendas Novas | 2024 | 2024 | 12 | 13 | 2024-03-18 | 0:00 | 2024-03-24 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.34 |  | < > | Setil | Vendas Novas | 2024 | 2024 | 15 | 16 | 2024-04-08 | 0:00 | 2024-04-14 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.35 |  | < > | Setil | Vendas Novas | 2024 | 2024 | 18 | 19 | 2024-04-29 | 0:00 | 2024-05-05 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.36 |  | < > | Setil | Vendas Novas | 2024 | 2024 | 21 | 22 | 2024-05-20 | 0:00 | 2024-05-26 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.37 |  | < > | Setil | Vendas Novas | 2024 | 2024 | 24 | 25 | 2024-06-10 | 0:00 | 2024-06-16 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.38 |  | < > | Setil | Vendas Novas | 2024 | 2024 | 27 | 28 | 2024-07-01 | 0:00 | 2024-07-07 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.39 |  | < > | Setil | Vendas Novas | 2024 | 2024 | 30 | 31 | 2024-07-22 | 0:00 | 2024-07-28 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.40 |  | < > | Setil | Vendas Novas | 2024 | 2024 | 33 | 34 | 2024-08-12 | 0:00 | 2024-08-18 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.41 |  | < > | Setil | Vendas Novas | 2024 | 2024 | 36 | 37 | 2024-09-02 | 0:00 | 2024-09-08 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.42 |  | < > | Setil | Vendas Novas | 2024 | 2024 | 39 | 40 | 2024-09-23 | 0:00 | 2024-09-29 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_03-0.43 |  | < > | Setil | Vendas Novas | 2024 | 2024 | 42 | 43 | 2024-10-14 | 0:00 | 2024-10-20 | 24:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Vendas Novas e Sinalização |  |  |  | 2021-12-23 | High | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_20_10-0.0 |  | < > | Pampilhosa | Guarda | 2021 | 2022 | 11 | 15 | 2021-03-08 | 0:00 | 2022-04-03 | 8:00 | 8h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Beira Alta |  |  |  | 2021-12-23 | Major | 1,2,3,4,5 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_20_10-0.1 |  | < > | Pampilhosa | Guarda | 2021 | 2022 | 11 | 15 | 2021-03-08 | 0:00 | 2022-04-03 | 0:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Beira Alta |  |  |  | 2021-12-23 | Major | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_20_14-1 |  | < > | Pampilhosa | Guarda | 2022 | 2022 | 15 | 53 | 2022-04-04 | 0:00 | 2022-12-31 | 24:00 | 24h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Beira Alta |  |  |  | 2021-12-23 | Medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_20_10-1.0 |  | < > | Pampilhosa | Guarda | 2023 | 2023 | 1 | 53 | 2023-01-01 | 0:00 | 2023-12-31 | 8:00 | 8h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Beira Alta |  |  |  | 2021-12-23 | Major | 1,2,3,4,5 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_20_10-1.1 |  | < > | Pampilhosa | Guarda | 2023 | 2023 | 1 | 53 | 2023-01-01 | 0:00 | 2023-12-31 | 0:00 | 48h | Periodical | Miscellaneous | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Modernização da Linha da Beira Alta |  |  |  | 2021-12-23 | Major | 6,7 | 1 |  |  |  |  | Publication | N
Infraestruturas de Portugal S.A. | 0094-MOD_37_25 |  | < > | Ermidas - Sado | Bifurcação de Torre Vã | 2021 | 2021 | 40 | 44 | 2021-10-01 | 1:00 | 2021-10-30 | 5:00 | 4h | Periodical | Catenary | T |  |  |  |  | ,, | ,, | ,, | ,, |  | Manutenção da infraestrutura de catenária |  |  |  | 2021-12-23 | Medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | Publication | N
ADIF | 2019-1-002 | Madrid Chamartín – Aranjuez (Getafe Industrial - Pinto) | ambos | Madrid Chamartín | Valencia Nord | 2023 | 2023 |  |  | 3º trimestre 2023 |  |  |  |  | Banda de mantenimiento | Getafe Industrial-Pinto: sustitución de traviesas RS por PR-01 |  | x | x | [7 empty] | implantación de LTV.
ADIF | 2019-1-005 | San Cristobal Industrial-Aranjuez | ambos | Madrid Chamartín | Valencia Nord | 2021 | 2023 |  |  | 2021 |  | 1º trimestre 2023 |  | 21 meses | Banda de mantenimiento y cortes extraordinarios | Proyecto Constructivo de Instalaciones de Seguridad y Comunicaciones para la adaptación del Bloqueo Automático Banalizado en el tramo San Cristóbal – Aranjuez de la línea 300 Madrid Chamartín – Valencia Estació del Nord | x | x | x | [7 empty] | Puesta en servicio del BAB. Está prevista la puesta en explotación en cuatro fases, empezando por Aranjuez y acabando por San Cristóbal Industrial. La primera fase empezaría en el segundo trimestre del año 2022 y cada tres meses tendríamos una fase, con lo que se finalizaría en el primer trimestre del año 2023. Cada fase comprende un corte total a las circulaciones por trayectos en fin de semana. Una semana antes del fin de semana de la Puesta en Explotación se cortan vías 3 y 5 de Ciempozuelos. FIN DE SEMANA DE PUESTA EN EXPLOTACIÓN (1º FASE): NOCHE DE VIERNES A SÁBADO:  HORARIO DE 22:00 A 10:00 Corte de vía 1 entre Ciempozuelos y Aranjuez. (Entre señales de entrada) Vía 2 funcionamiento normal.  DE 10:00 DEL SÁBADO A 00:00 DEL DOMINGO: Circulación con Bloqueo Telefónico por vía 1 Circulación con Bloqueo Automático por vía 2  DE LAS 00:00 DEL DOMINGO HASTA LAS 4:30 DEL LUNES: Corte total entre Valdemoro y Aranjuez con carga de software en Aranjuez, Ciempozuelos y CTC de Chamartín. Una vez finalizada carga de software, Aranjuez admite trenes lado sur hasta estacionamientos.  A PARTIR DE LAS 4:30 DEL LUNES BAB ENTRE CIEMPOZUELOS Y ARANJUEZ POR AMBAS VÍAS
ADIF | 2020-1-004 | Vicálvaro Merc. | ambos | Vicálvaro Merc | Vicálvaro Merc | 2020 | 2024 |  |  | 2020-02-01 |  | 1º trimestre 2024 |  | 48 meses | Todo el día | Remodelación integral estación | x | x | x | [7 empty] | Consta de 4 fases constructivas, habiendo finalizado la primera 1A. Restantes fases: 1B: Modificaciones accesos desde San Fernando y Vicálvaro para homogeneizar rampas con la máxima de líneas de Barcelona y Levante/AndaluCía, varias modificaciones en configuración de vías generales y de contorno, así como enlace con O'Donnell. 1C: Construcción nuevo haz de tráfico intermodal de 4 vías para operar trenes de 750 ms. 1D: Construcción 6 nuevas vías haz de llegadas de más de 750 ms. Modificación de la posición de las vías generales y de contorno de forma agrupada, eliminación de PN actual.
ADIF | 2021-1-001 | Estación de Aranjuez | ambos | Madrid Chamartín | Valencia Nord | 2021 | 2022 |  |  | agosto 2021 |  | marzo 2022 |  | 7 meses | banda de mantenimiento | Obras de acccesibilidad en la estación de Aranjuez, continuación de las ya ejecutadas que se encontraban paralizadas. |  |  | x | [7 empty] | Trabajos en borde de anden y en marquesinas de andenes en banda de mantenimiento.Posibles LTVs.
ADIF | 2021-1-007 | Alcázar-Manzanares | ambos | Alcázar de San Juan | Cadiz | 2022 | 2025 |  |  | 4º trimestre 2022 |  |  |  | 36 meses | Banda de mantenimiento y cortes extraordinarios | Instalación previa del BAB y sustitución enclavamiento de Manzanares. Posteriormente corte principal entre Herrera-Manzanares con actuación en vía y electrificación, con nueva variante, así como renovación completa de la estación de Herrera. Actuaciones de menor envergadura que quedaban pendientes de este proyecto en resto de trayectos. | x | x | x | [7 empty] | Primeros 6 meses sustitución enclavamiento de Manzanares y dotación BAB en trayecto, necesario algún corte extraordinario de fin de semana por definir. Restantes 30 meses, trabajos que quedaron pendientes en anterior actuación, teniendo especial relevancia el corte de una de las dos vías entre Herrera-Manzanares durante un período aún por definir, que sería la mayor parte de esta fase, teniendo una sola vía de circulación en dicho trayecto.
ADIF | 2021-1-008 | Aranjuez | ambos | Madrid Chamartín | Valencia Nord | 2023 | 2023 |  |  | 2023 |  | 2023 |  | 12 meses | Banda de mantenimiento y un corte extraordinario de 12 horas | Rehabilitación de catenaria con sustitución del hilo de contacto y sustentador en la cabecera lado Madrid y zona centro de la estación de Aranjuez | x | x | [8 empty] | Banda de mantenimiento y un corte extraordinario de 12 horas para sustitución pórticos sobre rio Tajo
ADIF | 2021-1-014 | Bif. Santa Catalina-Cercedilla-Escorial | ambos | Hendaya | Chamartín | 2022 | 2024 |  |  | 2º trimestre 2022 |  | 2024 |  | 24 meses | Banda de mantenimiento y posibles cortes extraordinarios sin definir | Renovación señalización en la red de cercanías zona norte. Sustitución de los enclavamientos desde Bif. Sta Catalina hasta El Escorial, y desde Villalba hasta Cercedilla. | x | x | [8 empty] | Banda de mantenimiento y posibles cortes extraordinarios Pendiente la firma del contrato.
ADIF | 2021-1-017 | Pinar-Las Matas | ambos | Hendaya | Madrid Chamartín | 2023 | 2026 |  |  | 1º trimestre 2023 |  | 1905-07-18 |  | 40 meses | Banda de mantenimiento y posibles cortes extraordinarios sin definir | Construcción 4 vías entre Pinar y Las Matas, y remodelación playa de vías de Pinar, para incremento de la capacidad tramo Pinar-Las Matas | x | x | x | [7 empty] | Fase 1 construcción cuadruple vía Pinar-Las Matas, duración 19 meses. Cortes extraordinarios totales de 4 horas cada uno en BM durante 51 días. Fase 2: remodelación playa vías Pinar, duración 21 meses. Cortes sucesivos permanentes de vías de estacionamiento con paso por rutas alternativas.
ADIF | 2021-1-020 | Estación de Pinto | ambos | Chamartín | Valencia Nord | [8 empty] | 21 meses | Banda de mantenimiento y posibles cortes extraordinarios sin definir | Construcción nuevo apeadero de La Tenería | x | x | x | [7 empty] | Trabajos por fases, en banda de mantenimiento cuando tenga afectación al tráfico. Modificación en vía e II.SS en acceso a la DP Citroen.
ADIF | 2021-1-021 | Estación de Puertollano | ambos | Ciudad Real | Badajoz | 2022 | 2023 |  |  | 3º trimestre 2022 |  | 1905-07-15 |  | 12 meses | proyecto de construcción de remodelación de la estación de Puertollano LAV+RC. Vía y Electrificación | Remodelación vías y andenes estación Puertollano | x | x | x | [7 empty] | Remodelación de playa de vías de Puertollano pasando una vía de ancho ibérico a ancho estándar. Hay 4 fases constructivas, con cortes de vías de estacionamiento alternativamente, que reducen la capacidad operativa durante la ejecución.
ADIF | 2021-1-022 | Estación de Navalperal | ambos | Hendaya | Chamartín | 2022 | 2023 |  |  | 3º trimestre 2022 |  | 4º trimestre 2023 |  | 15 meses | todo el dia | construcción paso inferior |  | x | x | [7 empty] | Fases constructivas: -Fase 1 (4.5 meses): trabajos con afectación al tráfico en BM (afectación tráfico mercancías). -Fase 2 (10,5 meses): corte de vías 1 y 2. Se instala un paso provisional para viajeros a cota de estas vías. Circulación por vías de apartado, trenes con parada comercial por vía 4.
ADIF | 2021-1-023 | Estación de Valdepeñas | ambos | Alcazar | Cádiz | 2022 | 2022 |  |  | 3º trimestre 2022 |  | 4º trimestre 2022 |  | 5 meses | todo el dia | construcción paso inferior |  | x | x | [7 empty] | Fases constructivas: Fase 1 (1.5 meses): trabajos con afectación al tráfico en BM (afectación tráfico mercancías). Fases 2 y 3 (3.5 meses) corte de vía 1 para construcción paso inferior y embocaduras. Circulación por vía 2.
ADIF | 2019-2-006 | Salamanca - Ftes Oñoro | ambos | Vilar-Formoso | Medina del Campo | 2020 | 2021 |  |  | ene.-2020 |  | 01/11/2022 |  | 35 meses |  | Electrificación y adaptación de 8 enclavamientos. Túnel de la Almedilla - Rebaje de vía por gálibo: realizado. |  | x | [8 empty] | TBA 396/20 (12/12/20 al 11/11/22 ) y TBA 391/20 (01/03/21 al 11/11/22). Trabajos de electrificación en ejecución (en este momento centrados en Estación de Salamanca). Trabajos en ENCEs en ejecución, con previsión de inicio PeS a partir mayo 2022 implicando repartir el trayecto en tres tramos y se dejará en bloqueo telefónico el tramo en el que se carguen los enclavamientos. La afección será la que corresponda a un bloqueo telefónico de tres estaciones. Las actuaciones se iniciarán a partir de diciembre de 2021 y la duración será de una semana por trayecto. ojo trafico internacional
ADIF | 2021-2-008 | Gomecello | ambos | Vilar-Formoso | Medina del Campo | 2020 | 2021 |  |  | mar.-2020 |  | 01/07/2022 |  | 28 meses |  | Construcción paso inferior 64,466 y supresión P/N 63,824. |  |  | x | [7 empty] | LTV´s a 30 Km/h.desde el Km 64/350 al 64/550, hasta final obra. TBA 88/20 (18/03/20 al 31/01/22). Se espera hacer el paso inferior en enero y finalizarlo en febrero.
ADIF | 2021-2-015 | Salamanca - Ftes Oñoro | ambos | Vilar-Formoso | Medina del Campo | 2022 | 2022 |  |  | 2022-04-01 |  | nov-22 |  | 8 meses |  | Sustitución de traviesas de madera pte. Padrillo, (MIV). Demolición estructuras pasos superiores sustituidos en obra de gálibos. | x | [9 empty] | Entre Salamanca - Tejares interrupción de la circulación entre las 08:00 h. y las 20:00 h. Previsto domingos 24/04 y 01/05
ADIF | 2021-2-016 | Salamanca - Ftes Oñoro | ambos | Vilar-Formoso | Medina del Campo | 2022 | 2022 |  |  | oct.-2021 |  | 01/11/2022 |  | 12 meses |  | Obra de gálibos Salamanca - Fuentes Oñoro. Construcción de pasos superiores. Quedan un total de 5 pasos entre Salamanca y Fuentes. |  |  | x | [7 empty] | Entre Salamanca - Tejares, No está previsto corte, sólo se implantarán LTVs de 60 km/h para protección de los trabajos (demolición y reconstrucción). máximo 2 limitaciones en toda la línea. Los pasos se ejecutarán de uno en uno. Esta actuación se va a paralizar por un modificado en curso.
ADIF | 2019-3-006 | San Pablo - Almoraima (p.k. 129/400 al 155/438) | ambos | Bif. Las Maravillas | Algeciras | 2019 | 2022 |  |  | 2019-05-01 |  | 1º trim. 2022 |  | 31,5 meses | - | Renovacion del tramo San Pablo - Almoraima (línea Bobadilla - Algeciras), entre los p.k. 129/400 y 155/438 |  |  | x | [7 empty] | Obras realizadas al amparo de TBA. No va a necesitar corte de vía (SO Sur).
ADIF | 2020-3-010 | Ampliación de la longitud útil de vía a 750 m en los apartaderos de Campillos y Setenil, del tramo Bobadilla – Algeciras |  | Bobadilla | Algeciras | 2021 | 2024 |  |  | 2º trimestre 2022 |  | 4º trimestre 2023 |  | 19 meses |  | Ampliación de vías de apartado a 750 m de longitud útil en las estaciones de Campillos y Setenil. |  | x | [8 empty] | Trabajos en BM + otros intervalos que pueda conceder el PM. Necesidad de CVE en distintas fases de obra y de distinta duración. 2022 Estación de Campillos: Fase 2 JUNIO CVE (3 días), OCTUBRE Fase 4 CVE (1 día). 2023 Estación de Setenil: Fase 2b MARZO (8 horas), Fase 3 JUNIO (2 días) y Fase 4 JULIO (8h).
ADIF | 2020-3-013 | Estaciones de Cáceres, Mérida Aljucén y Badajoz.l026: Cáceres Frontera: Tramos: Bfif. Casa de La torre - Bif. Romanos, Bif. Granja- Las Encinas -Aljucén, Aljucén - La Garrovilla, Bif. San Nicolás Badajoz, Badajoz Frontera |  | Cáceres - | Frontera Portuguesa | - | - |  |  | 2021-12-01 |  | 01/08/2023 |  |  |  | Renovación de acceso y estaciones de Cáceres, Merida, Aljucén y Badajoz y tramo Badajoz frontera Portuguesa | [10 empty] | LTV´s vigentes según TBA 5151/21 en Badajoz-Frontera a partir de febrero, y previstas en la estación de Badajoz a partir de marzo
ADIF | 2021-3-006 | Montijo |  | Ciudad Real | Badajoz | 2022 | 2022 |  |  | Segundo trimestre 2022 |  | Tercer trimestre 2022 |  | 95 h |  | Sustitución marco P.K. 475+200 | x | [9 empty] | Corte total de circulación durante 95 h
ADIF | 2021-3-010 | P.P.K.K. 513+689 y 515+891 |  | Badajoz | Km 517,6 Frontera Portuguesa | 2021 | 2022 |  |  | segundo trimestre 2022 |  | tercer trimestre 2022 |  | 3 semanas |  | Colocación de Escape en vía general en el P.K 513+689 y desvío en el P.K. 891. | x |  | x | [7 empty] | Corte de 12h/24h en fin de semana para colocar los aparatos de vía. 24h de LTV a 30km/h.+ 24h a 60km/h.+ 48h a 80km/h. + 2 semanas para finalizar actuación
ADIF | 2021-3-015 | P.K. 458+723 |  | Ciudad Real | Badajoz | 2022 | 2022 |  |  | 1er trimestre 2022 |  | 3er tirmestre 2022 |  | 6 meses |  | SUPRESIÓN DEL PASO A NIVEL EN EL ACCESO A ALJUCEN - MÉRIDA SITUADO EN LA LÍNEA CONVENCIONAL | x |  | x | [7 empty] | Durante la construcción del paso superior y posterior supresión del paso a nivel, limitaciones de velocidad, un corte nocturno para colocar las vigas y prelosas y posiblemente otro para desmontar el paso a nivel.
ADIF | 2021-3-028 | Espeluy-Lora del Río |  |  |  | 2022 | [9 empty] | SUSTITUCIÓN DE CARRIL INÚTIL T/ESPELUY-LORA DEL RÍO. OBRA
ADIF | 2021-3-032 |  |  | Bobadilla | Ronda | 2023 | 2023 | [6 empty] | 4 meses |  | TRATAMIENTO DE LA LADERA DE ALMARGEN. TRAYECTO ALMARGEN - SETENIL
ADIF | 2021-3-036 |  |  | Villanueva Serena | Brazartortas | 2022 | 2024 |  |  | 2022-10-01 |  | sep-24 |  | 23 meses |  | SUPRESIÓN DE BLOQUEO TELEFÓNICO ENTRE VILLANUEVA DE LA SERENA – BRAZATORTAS/VEREDAS
ADIF | 2022-3-001 | Jimena de la Frontera |  | Bif. Las Maravillas | Algeciras | 2022 | 2023 |  |  | 2022-11-01 |  | 01/12/2023 |  |  |  | Actuación integral en playa de vías y andenes de Jimena de la Frontera y reposición de pasos superiores por gálibos para electrificación futura | x | x | [8 empty] | Trabajos en BM + otros intervalos que pueda conceder el PM. Necesarios varios cortes de vía total (rebaje de plataforma y desvíos en vía general, y zonas de Paso Superiores) y corte de circulación por fases en las vías de Jimena. Coordinación con las obras de CMS. Cortes de vía total: *8h. Paso Sup (sept-22) *83h. Rebaje de plataforma y PS (nov 2022) *12h desvio 2 y PS (dic-22) *8h. Paso Sup (feb -23) *12h Desvío 1 (mayo-23) Cortes de vía general y auxiliares para la renovación por fases SIN corte total de circulación (enero/mayo 2023)
ADIF | 2022-3-002 | Campillos-Setenil |  | Bif. Las Maravillas | Algeciras | 2023 | 2024 |  |  | 2023-01-01 |  | feb-24 |  |  |  | EJECUCIÓN DE LAS OBRAS DE AMPLIACIÓN DE LA LONGITUD A 750 METROS DE LOS APARTADEROS DE CAMPILLOS Y SETENIL EN EL TRAMO BOBADILLA-RONDA | x | [9 empty] | 05/11/2021: Trabajos en BM + otros intervalos que pueda conceder el PM. Necesidad de CVE en distintas fases de obra y de distinta duración. Estación de Campillos: Fase 2 Enero 2023 CVE (3 días), Fase 4 Mayo 2023 CVE (1 día). Estación de Setenil: Fase 2b Noviembre 2023 (8 h) Fase 3 Enero 2024 CVE (2 días) Fase 4 Febrero 2024 (8h)
ADIF | 2022-3-004 | Calancha-Vilches |  |  |  | 2023 |  |  |  | 2021-11-01 |  | jun-23 |  |  |  | ACTUACIÓN CORRECTORA TUNEL 10 |  | x | [8 empty] | Se ha solicitado TBP del 7 al 31 de Marzo del 2022 con el que se amplía la BM.
ADIF | 2019-6-001 | Hendaya – Alsasua | ambos | Hendaya | Madrid Chamartín | 2017 |  |  |  | 4 trimestre 2021 |  | 4 trimestre 2024 |  | 34 meses | - | Implantación del ancho mixto en el tramo Astigarraga – Irún y estación de Irún. (Obra transferida desde Adif – AV). | x | x | x | [7 empty] | Entre Rentería e Irún: Trabajos de ampliación de gálibo en túnel de Gaintxurizqueta. Obra de vía paralizada temporalmente en situación de corte total de vía 2 entre Lezo e Irún. Banda de Mantenimiento con intervalo adicional nocturna (con TBA). Continúan trabajos de IISS y LAC en corte nocturno. Cortes extraordinarios de fin de semana según fases de proyecto. En 2022 previsto: - Fin de semana del 4/06 al 5/06 (53 horas). Entre Hernani y San Sebastián. Escape Loiola Entre Rentería e Irún. Demolición de Pasos Superiores de Nafarroa y Araso - Fin de semana del 25/06 al 26/06 (53 horas) Apeadero de Ventas. Demolición de Teilería - Fin de semana del 23/07 al 25/07 (77 horas) Estación Hernani - Fin de semana 9/09 al 11/09 (77 horas) Entre San Sebastián y Pasajes. Doble escape de Ategorrieta Entre Hernani y Pasajes trabajos de ampliación de gálibo en túnel de Loiola. Previsto corte total de vía 2 (año 2023) Corte extraordinario de 6 semanas de duración para ampliación de gálibo en túnel de Capuchinos, nuevas estructuras en Glorieta de Buenavista, nueva estructura en Paso Inferior de Misericordia y actuación en puente de Oiartzun (año 2024)
ADIF | 2019-6-002 | Hendaya – Alsasua | ambos | Hendaya | Madrid Chamartín | 2017 | 2021 |  |  | 2017-03-01 |  | dic-21 |  | 52 meses | - | Sustitución del enclavamiento de la estación de Irun | x | x | [8 empty] | Cortes extraordinarios de fin de semana según fases del proyecto.
ADIF | 2019-6-005 | Hendaya – Alsasua | ambos | Hendaya | Madrid Chamartín | 2017 | 2022 |  |  | 2017-03-01 |  | 01/03/2022 |  | 50 meses | - | Adaptación de Instalaciones de Seguridad y Comunicaciones para implantación del ancho estandar en el trayecto Hernani - Irun | x | x | [8 empty] | Banda de Mantenimiento con intervalo adicional.
ADIF | 2019-6-007 | Hendaya – Alsasua | ambos | Hendaya | Madrid Chamartín | 2021 | 2021 |  |  | 2021-03-01 |  | dic-21 |  | Terminada |  | Construcción de paso inferior en la C/ Iztueta de San Sebastian. | x | x | x | [7 empty] | Están urbanizando el entorno de Iztueta sin afectación al tráfico ferroviario
ADIF | 2019-6-010 | Hendaya – Alsasua | ambos | Hendaya | Madrid Chamartín | 2018 | 2022 |  |  | 2018-03-11 |  | 01/04/2022 |  | 44 meses | - | Ejecución paso inferior, ascensores y recrecido de andenes en el apeadero de Urnieta |  | x | x | [7 empty] | LTV a 30/60 km/h. Banda de Mantenimiento con intervalo adicional. Está pendiente de la puesta en servicio del paso inferior para poder hacer el levantado del paso a nivel con su correspondiente recrecido de anden. (Preparando documentación para mandar al inspector de ministerio)
ADIF | 2019-6-011 | Hendaya – Alsasua | ambos | Hendaya | Madrid Chamartín | 2018 | 2022 |  |  | 2018-10-01 |  | may-22 |  | 41 meses | - | Ejecución paso inferior, ascensores y recrecido de andenes en la estación de Andoain |  | x | x | [7 empty] | LTV a 30/60 km/h. Banda de Mantenimiento con intervalo adicional. Se ha enviado documentación a la inspección para la recepción de la obra de paso inferior, vamos a intentar recepcionarla el día 23 de diciembre. Una vez recepcionada se continuaran con los trabajos de levantado de paso a nivel y recrecido de esta zona a partir de enero, esperamos terminar para finales de febrero y poder en marzo eliminar la limitación de velocidad.
ADIF | 2019-6-012 | Hendaya – Alsasua | ambos | Hendaya | Madrid Chamartín | 2018 | 2022 |  |  | 2018-10-01 |  | 30/09/2022 |  | 48 meses | - | Ejecución recrecido de andenes en el apeadero de Ordizia |  | x | x | [7 empty] | LTV a 30/60 km/h. Banda de Mantenimiento con intervalo adicional. La obra del recrecido de andenes se finalizó, pero debido a la peligrosidad del paso a nivel existente se tiene que mantener la limitación de velocidad hasta que se ejecute el paso inferior. Las obras del paso inferior están en licitación.
ADIF | 2019-6-013 | Hendaya – Alsasua | ambos | Hendaya | Madrid Chamartín | 2022 | 2022 |  |  | 2022-01-05 |  | dic-22 |  | 12 meses | - | Recrecido de andenes con ripado de vía e instalación de ascensores en la estación de Billabona-Zizurkil |  | x | x | [7 empty] | LTV a 30/60 km/h. Banda de Mantenimiento con intervalo adicional. No se acometerá la obra hasta el año 2022,. A la espera de un modificado técnico.
ADIF | 2019-6-015 | Hendaya – Alsasua | ambos | Hendaya | Madrid Chamartín | 2022 | 2022 |  |  | 2022-01-15 |  | 31/03/2022 |  | 3 meses | - | Rehabilitación de vía y mejora de parámetros de vía en túnel de Zumarraga PK 566/128 PK 566/846 T/Zumarraga-Gabiria . |  | x | x | [7 empty] | Afectación prevista: Intervalo extraordinario de 2 jornadas ( fin de semana) ambas vias . Banda de Mantenimiento con intervalo adicional Limitaciones a 30 y 60 km/h. Por la otra vía limitaciones a 30 km/h por protección de trabajos. Se está tramitando expediente gesto 508/21 MI-TP1 en borrador .Fechas 19/03 al 21/03 de 2022.
ADIF | 2019-6-016 | Hendaya – Alsasua | ambos | Hendaya | Madrid Chamartín | 2022 | 2022 |  |  | 2022-02-15 |  | jul-22 |  | 5 meses | - | Rehabilitación de vía y mejora de parámetros de vía en túnel de Osina PK 551/232 PK 551/939 T/Otzaurte-Brinkola |  | x | x | [7 empty] | Afectación prevista: Intervalo extraordinario de 4 jornadas ( fin de semana) Banda de Mantenimiento con intervalo adicional Limitaciones a 30 y 60 km/h. Por la otra vía limitaciones a 30 km/h por protección de trabajos. Obra paralizada. Nueva redacción de proyecto. No se acometerá la obra previsiblemente hasta el año 2022
ADIF | 2019-6-022 | Miranda de Ebro – Venta de Baños | ambos | Hendaya | Madrid Chamartín | 2022 | 2022 |  |  | 2022-06-01 |  | 30/09/2022 |  | 2 meses | - | Renovación de vía 8 en la estación de Pancorbo |  | x | [8 empty] | Corte de vía 8 y corte de tensión que puntualmente afectará a las vías pares de la estación
ADIF | 2019-6-023 | Miranda de Ebro – Venta de Baños | ambos | Hendaya | Madrid Chamartín | 2022 | 2022 |  |  | 2022-06-01 |  | sep-22 |  | 2 meses | - | Renovación de vía 6 en la estación de Calzada de Bureba |  | x | [8 empty] | Corte de vía 6 y corte de tensión que puntualmente afectará a las vías pares de la estación
ADIF | 2019-6-037 | Bilbao - Orduña | ambos | Bilbao Abando | Casetas | 2022 | 2023 |  |  | 2022-04-01 |  | abr-23 |  | 12 meses | - | Ejecución paso inferior, ascensores y recrecido de andenes en la estación de Amurrio |  |  | x | [7 empty] | LTV a 30 km/h . Se tiene que modificar el proyecto, y licitarlo, por lo que se preveé que se empiecen las obras en septiembre de 2021. La duración será tambien 12 meses. Banda de Mantenimiento con intervalo adicional para el montaje de apeos. Sin prevision de Inicio, contrata responsable no inicia trabajos por sobrecostes en el contrato
ADIF | 2020-6-002 | Miranda de Ebro – Venta de Baños | ambos | Hendaya | Madrid Chamartín | 2022 | 2022 |  |  | 2022-03-15 |  | sep-22 |  | 6 meses |  | Tratamiento de trinchera PK 444/300 al 444/650 entre Pancorbo y Bujedo | x | x | x | [7 empty] | Limitaciones a 30 km/h y 60 km/h en las dos vías mientras duren los trabajos. Ampliación de Banda de Mantenimiento. Posible afección a viajeros. Sin previsión de transbordos. Ampliación de intervalo de trabajo en Banda de Mantenimiento y trabajos en fin de semana. Se está redactando una nueva ACP por emergencia para realizar el trabajo. Posible corte extraordinario de fin de semana en ambas vías, ya que la solución puede ser la construcción de un túnel artificial. Continua en estudio la posible solucion. Sin previsión de inicio. Actualmente se ha establecido una LTV a 30km/h por mal estado del talud, estudiándose un posible aumento a 50km/h próximamente. Proyecto pendiente de redacción. Se actualizará la información en el 2º semestre de 2022
ADIF | 2020-6-005 | Hendaya – Alsasua | ambos | Hendaya | Madrid Chamartín | 2022 | 2023 |  |  | 2022-01-01 |  | 01/12/2023 |  | 19 meses |  | Conexión de la N.R.F.P.V- con la RED convencional de ADIF en el T/Hernani -San Sebastian para implantación del ancho estandar. | x | x | x | [7 empty] | Banda de Mantenimiento con intervalo adicional. Cortes de vía extraordinarios de fines de semana si fuera necesario. Se está tramitando expediente gesto 517/21 MI TB-1 en borrador. Fechas 19/03 al 21/03 de 2022.
ADIF | 2020-6-015 | Venta de Baños - Ávila | ambos | Hendaya | Madrid Chamartín | 2020 | 2022 |  |  | 2020-08-01 |  | jun-22 |  | 24 meses |  | Montaje vía y electrificación Variante Valladolid |  |  | x | [7 empty] | Banda de mantenimiento y cortes extraordinarios de vía. Se han ha reanudado las actuaciones y las afecciones a la RC solo afectaran en un principio al ramal Valladolid- La Carrera y cuando nos lo soliciten.
ADIF | 2020-6-016 | Hendaya – Alsasua | ambos | Hendaya | Madrid Chamartín | 2022 | 2022 |  |  | 2022-09-01 |  | 01/12/2022 |  | 4 meses |  | Tratamiento de terraplén PK 568/475 entre Zumarraga y Gabiria |  |  | x | [7 empty] | Banda de Mantenimiento con intervalo adicional y limitaciones a 30 km/h. Cortes de tensión si fuera necesario
ADIF | 2020-6-019 | Alsasua - Miranda de Ebro | ambos | Hendaya | Madrid Chamartín | 2022 | 2022 |  |  | 2022-02-01 |  | abr-22 |  | 2 meses |  | Sustitución de carril en barra larga por desgaste y antigüedad entre Miranda y Nanclares |  |  | x | [7 empty] | Banda de Mantenimiento con intervalo adicional Limitaciones a 30 y 60 km/h. Por la otra vía limitaciones a 30 km/h por protección de trabajos
ADIF | 2020-6-037 | Hendaya - Alsasua | ambos | Hendaya | Madrid Chamartín | 2020 | 2023 |  |  | 2020-10-01 |  | abr-23 |  | 54 meses | - | Remodelación de la estación de Atocha en San Sebastián, por las obras de el enganche de Alta velocidad |  | x | x | [7 empty] | Supresión y modificación de vías en cinco fases de construcción. Han empezado a levantar vías secundarias en la estación de San Sebastián. Fin de semana del 19/06 al 21/06 colocacion de pasarela .Expediente Gesto nº137/21.corte total de vias de las 00.00 del 19 a las 04,00 del 21.
ADIF | 2021-6-004 | Miranda - Venta de Baños | ambos | Hendaya | Madrid Chamartín | 2021 | 2022 |  |  | 2021-10-01 |  | ene-22 |  | 3 meses | - | Sustitución de carril en barra larga por desgaste y antigüedad entre Quintana del Puente y Villodrigo |  |  | x | [7 empty] | Banda de Mantenimiento con intervalo adicional Limitaciones a 30 y 60 km/h. Por la otra vía limitaciones a 30 km/h por protección de trabajos. Pendiente de ACP
ADIF | 2021-6-005 | Miranda - Venta de Baños | ambos | Hendaya | Madrid Chamartín | 2021 | 2022 |  |  | 2021-10-31 |  | 15/02/2022 |  | 3 meses | - | Sustitución de carril en barra larga por desgaste y antigüedad entre Villaquirán y Estepar |  |  | x | [7 empty] | Banda de Mantenimiento con intervalo adicional Limitaciones a 30 y 60 km/h. Por la otra vía limitaciones a 30 km/h por protección de trabajos. Pendiente de ACP
ADIF | 2021-6-013 | San Sebastián - Hendaya | ambos | Hendaya | Madrid Chamartín | 2021 | 2022 |  |  | 2021-03-15 |  | 15/04/2022 |  | 12 meses | - | Recrecido de andenes y paso inferior en Apd Herrera |  |  | x | [7 empty] | LTV a 30/60 km/h. Banda de Mantenimiento con intervalo adicional.
ADIF | 2021-6-015 | Andoain - San Sebastián | ambos | Hendaya | Madrid Chamartín | 2021 | 2022 |  |  | 2021-04-15 |  | abr-22 |  | 12 meses | - | Recrecido de andenes y paso inferior en Apd Hernani Centro |  |  | x | [7 empty] | LTV a 30/60 km/h. Banda de Mantenimiento con intervalo adicional.
ADIF | 2021-6-016 | Brinkola - Altsasu | ambos | Hendaya | Madrid Chamartín | 2021 | 2021 |  |  | 2021-06-01 |  | 30/09/2021 |  | Terminada | - | Rehabilitación de vía y mejora de parámetros de vía en túnel de Osineta 548/124 - 548/850 .Otzaurte-Brinkola. |  |  | x | [7 empty] | Afectación prevista: Intervalo extraordinario de 4 jornadas ( fin de semana) Banda de Mantenimiento con intervalo adicional Limitaciones a 30 y 60 km/h. Por la otra vía limitaciones a 30 km/h por protección de trabajos .
ADIF | 2021-6-017 | Zumarraga - Brinkola | ambos | Hendaya | Madrid Chamartín | 2022 | 2023 |  |  | 2022-01-15 |  | may-23 |  | 13 meses | - | Ejecución recrecido de andenes y paso inferior en el apeadero de Legazpi PK 561/126 |  |  | x | [7 empty] | LTV a 30/60 km/h. Banda de Mantenimiento con intervalo adicional. En 2022 se van a iniciar trabajos de micropilotaje a finales de Enero, por lo que será necesario establecer una limitación de velocidad. Una vez que sepamos la fecha concreta de los trabajos se solicitara dicha limitación.
ADIF | 2021-6-019 | Castejón -Cortes de Navarra | ambos | Casetas | Bilbao Abando | 2021 | 2021 |  |  | 2021-01-15 |  | feb-21 |  | Terminada | - | Sustitución de traviesas entre Tudela y Castejón Via II |  |  | x | [7 empty] | Banda de Mantenimiento con intervalo adicional Limitaciones a 30/60/90 km/h. Por la otra vía limitaciones a 60 km/h por protección de trabajos
ADIF | 2021-6-022 | Medina del Campo - Ávila | ambos | Hendaya | Madrid Chamartín | 2021 | 2021 |  |  | 2021-04-08 |  | 30/06/2021 |  | Terminada | - | Sustitución carril Distrito de Arévalo vías I y II (AMNR) |  |  | x | [7 empty] | LTV a 30 Km/h. proteccion trabajos vía contigua, banda mantenimiento nocturna
ADIF | 2021-6-023 | Valladolid - Medina del Campo | ambos | Hendaya | Madrid Chamartín | 2021 | 2021 |  |  | 2021-04-08 |  | jul-21 |  | Terminada | - | Sustitución carril Distrito de Medina del Campo vías I y II (AMNR) |  |  | x | [7 empty] | LTV a 30 Km/h. proteccion trabajos vía contigua, banda mantenimiento nocturna.
ADIF | 2021-6-024 | Medina del Campo - Ávila | ambos | Hendaya | Madrid Chamartín | 2021 | 2021 |  |  | 2021-10-01 |  | 22/12/2021 |  | 2 meses | - | Sustitución traviesas RS x PR01 vía I y II del 173/000 al 173/944 Arévalo - Ataquines (AMNR) |  |  | x | [7 empty] | LTV a 30/60 Km/h. Banda de mantenimiento, corte tensión para descarga y sustitución
ADIF | 2021-6-025 | Medina del Campo - Ávila | ambos | Hendaya | Madrid Chamartín | 2022 | 2022 |  |  | 2022-05-01 |  | jun-22 |  | 2 meses | - | Desguarnecido mecanizado por trayectos en vías I y II en el distrito de Arévalo (AMNR) |  |  | x | [7 empty] | LTV a 30/60 Km/h. Banda de mantenimiento, corte tensión
ADIF | 2021-6-026 | Estación de Valladolid | ambos | Hendaya | Madrid Chamartín | 2021 | 2021 |  |  | 2021-04-01 |  | 15/06/2021 |  | Terminada | - | Renovacion de vía acceso al deposito de Valladolid Campo Grande (AMNR) |  | x | [8 empty] | Intervalos de trabajos consensuados con con la estación
ADIF | 2021-6-027 | Estación de Venta de Baños | ambos | Hendaya | Madrid Chamartín | 2021 | 2021 |  |  | 2021-04-01 |  | jun-21 |  | Terminada | - | Renovacion de vías 25,27 y varias desvios de la estación de Venta de Baños (AMNR) |  | x | [8 empty] | Intervalos de trabajos consensuados con con la estación.
ADIF | 2021-6-028 | Orduña - Bilbao Abando | ambos | Casetas | Bilbao Abando | 2022 | 2022 |  |  | 2022-03-01 |  | 30/12/2022 |  | 7 meses | - | Tratamiento y obras de mejora de las trincheras comprendidas entre los P.K. 236/700 al 237/100 entre Miraballes y Arrigorriaga |  |  | x | [7 empty] | LTV a 30/60 km/h. Banda de Mantenimiento con intervalo adicional con trabajos diurnos siempre que sea posible y corte de tensión si fuera necesario (trabajos en altura)
ADIF | 2021-6-029 | Orduña - Bilbao Abando | ambos | Casetas | Bilbao Abando | 2022 | 2022 |  |  | 2022-03-01 |  | jun-22 |  | 2 meses | - | Sustitución de carril entre Arrigorriaga y Ollargan |  |  | x | [7 empty] | LTV a 30 Km/h en la vía que se trabaja. Banda de Mantenimiento con intervalo adicional
ADIF | 2021-6-037 | Burgos - Quintanapalla | ambos | Madrid | Hendaya | 2021 | 2021 |  |  | 2021-10-01 |  | dic-21 |  | Terminada | - | Saneamiento de abombamientos en zonas gunitadas en el túnel 1 de la Brújula. (A la espera de la solución a adoptar por Jefatura de Túneles) |  |  | x | [7 empty] | imitaciones a 30 km/h en las dos vías mientras duren los trabajos con corte de tensión. Ampliación de Banda de Mantenimiento. Visitada la obra por todas las partes responsables. En estudio la solución a consensuar con la SD de Infraestructura y Vía. Sin previsión de inicio, pero con toda probabilidad se ejecutará este año.
ADIF | 2021-6-038 | Quintana del Puente | ambos | Madrid | Hendaya | 2022 | 2022 |  |  | 2022-04-15 |  | 30/06/2022 |  | 2 meses | - | Sustitución de desvíos AxC con traviesas sintéticas en la cabecera sur y materiales convencionales en la cabecera norte en la estación de Quintana del Puente |  | x | x | [7 empty] | Banda de Mantenimiento con intervalo adicional más intervalos extraordinarios de fin de semana para montar los cuerpos centrales de los escapes necesitando entre 4 a 6 horas de corte para ambas vias. Limitaciones a 30 y 60 km/h según avance de la obra. Por vía contraria siempre limitaciones a 30 km/h por protección de trabajos. Sin previsión exacta. Elaborando proyecto ACP. Obra promovida por la Gerencia de Área de Vía (J. A. Rivas) con traviesas sintéticas. con traviesas sintéticas en la cabecera sur y materiales convencionales en la cabecera norte. Las dos fases están contratadas. Materiales ya pedidos.Hay retrasos en la entrega de materiales
ADIF | 2021-6-039 | Valladolid C.G. - Tres Hermanos | ambos | Madrid | Hendaya | 2021 | 2022 |  |  | 2021-02-01 |  | ene-22 |  | 10 meses | - | Proyecto de construcción del Paso Inferior entre las calles Nochevieja y Andrómeda en el P.K. 250/970 entre Valladolid C.G. y Tres Hermanos | x | x | x | [7 empty] | LTV a 30 km/h. Se están terminando los últimos retoques de la obra
ADIF | 2021-6-040 | Llodio | ambos | Casetas | Bilbao Abando | 2021 | 2022 |  |  | 2021-09-01 |  | 15/03/2021 |  | 6 meses | - | Recrecido de andenes estación de Llodio |  |  | x | [7 empty] | LTV a 30 km/h. Banda de Mantenimiento con intervalo adicional.
ADIF | 2021-6-041 | Bilbao Mercancias | ambos | Santurtzi | Bilbao Mercancias | 2021 | 2022 |  |  | 2021-03-01 |  | feb-22 |  | 10 meses | - | Nuevo Paso Superior en muelles del Puerto (pp.kk. 16/280). Estación Bilbao Mercancias. | x | [9 empty] | Trabajos con Banda de Mantenimiento con intervalo adicional. Se está hormigonando el nuevo paso superior y acabar los últimos remates
ADIF | 2021-6-042 | San Sebastián | ambos | Madrid | Hendaya | 2021 | 2021 |  |  | 2021-04-15 |  | 15/08/2021 |  | Terminada | - | Obra del proyecto de ejecución de demolición de edificaciones Calle Mundaiz 14 W y 18 en la estación de San Sebastián. |  | x | [8 empty] | Estas obras se desarrollan en el mismo ámbito de las obras de la estación de Atotxa y entendemos que están entre los PKs 622.000 y 622.150. Se está pendiente del desalojo de los edificios para poder iniciar los trabajos. Cuando se inicien se solicitará limitación de velocidad y corte de tensión durante los trabajos nocturnos. En ejecución
ADIF | 2021-6-043 | Quintana del Puente - Quintanilleja | ambos | Madrid | Hendaya | 2022 | 2022 |  |  | 2022-04-30 |  | jun-22 |  | 3 meses | - | Sustitución de traviesas y carril entre Quintana del Puente y Quintanilleja. |  |  | x | [7 empty] | LTV a 30/60 km/h. Banda de Mantenimiento con intervalo adicional con trabajos diurnos siempre que sea posible, y corte de tensión en descarga. Sin previsión de inicio (Jefatura de C. Inv.). Se realizó la propuesta de inversión. Sin conocimiento de cómo van los plazos de tramitación.
ADIF | 2021-6-046 | Avila - Venta de Baños | ambos | Madrid | Hendaya | 2022 | 2023 |  |  | 2022-04-01 |  | 31/10/2023 |  | 18 meses | - | Proyecto de construcción de tres Pasos Inferiores en las calles panaderos y Labradores en la estación de Valladolid C.G. | x | x | x | [7 empty] | LTV a 30 km/h con corte extraordinario de vía en fines de semana. Todavía se está consensuando con el Ayuntamiento la planificación de la obra para elaborar un GESTO
ADIF | 2021-6-047 | Avila - Venta de Baños | ambos | Madrid | Hendaya | 2021 | 2022 |  |  | 2021-11-01 |  | ene-22 |  | 3 meses | - | Sustitución carril Distrito de Medina del Campo vía I (AMNR) |  |  | x | [7 empty] | LTV a 30 Km/h. proteccion trabajos vía contigua, banda mantenimiento nocturna
ADIF | 2021-6-048 | Avila - Venta de Baños | ambos | Madrid | Hendaya | 2021 | 2022 |  |  | 2021-11-01 |  | 30/01/2022 |  | 4 meses | - | Sustitución carril Distrito de Arévalo vía I (AMNR) |  |  | x | [7 empty] | LTV a 30 Km/h. proteccion trabajos vía contigua, banda mantenimiento nocturna
ADIF | 2021-6-049 | Avila - Venta de Baños | ambos | Madrid | Hendaya | 2022 | 2022 |  |  | 2022-05-01 |  | jun-22 |  | 3 meses | - | Sustitución de traviesas RS por PR-VE en el tramo Adanero - Arévalo vía II (ACP) |  |  | x | [7 empty] | LTV a 30 Km/h. proteccion trabajos vía contigua, banda mantenimiento nocturna
ADIF | 2021-6-050 | Avila - Venta de Baños | ambos | Madrid | Hendaya | 2022 | 2022 |  |  | 2022-05-01 |  | 30/06/2022 |  | 3 meses | - | Renovación de traviesas entre los PP.KK. 157+407 - 159+793 en el tramo Ávila - Medina del Campo vía I (ACP) |  |  | x | [7 empty] | LTV a 30 Km/h. proteccion trabajos vía contigua, banda mantenimiento nocturna
ADIF | 2021-6-051 | Magaz - Bifurcación Villamuriel | ambos | Magaz | Palencia Arroyo Villalobon | 2022 | 2022 |  |  | 2022-05-01 |  | jun-22 |  | 3 meses | - | Sustitución de traviesas entre los PP.KK. 5+212 y 4+081 de la vía I y II en el By Pass de Magaz (ACP) |  |  | x | [7 empty] | LTV a 30 Km/h. proteccion trabajos vía contigua, banda mantenimiento nocturna
ADIF | 2021-6-052 | Venta de Baños - Burgos Rosa de LIma | ambos | Madrid | Hendaya | 2021 | 2022 |  |  | 2021-10-15 |  | 30/01/2022 |  | 3 meses | - | Renovación parcial de materiales vía tramo Quintana del Puente - Villodrigo - Villaquirán por vía II. |  |  | x | [7 empty] | Banda de Mantenimiento con intervalo adicional Limitaciones a 30 y 60 km/h. Por la otra vía limitaciones a 30 km/h por protección de trabajos.
ADIF | 2021-6-053 | Burgos Rosa de Lima - Miranda de Ebro | ambos | Madrid | Hendaya | 2021 | 2022 |  |  | 2021-11-15 |  | feb-22 |  | 3 meses | - | Sustitución de carril por defectos graves en diversos puntos entre el PK 317/672 y el 468/350. |  |  | x | [7 empty] | Banda de Mantenimiento con intervalo adicional Limitaciones a 30 y 60 km/h. Por la otra vía limitaciones a 30 km/h por protección de trabajos.
ADIF | 2021-6-055 | San Sebastián - Irun | ambos | Madrid | Hendaya | 2021 | 2023 |  |  | 2021-10-01 |  | jun-23 |  | 19 meses | - | Proyecto de ampliación de la longitud útil de las vías 3,5,7 y 9 en la estación de Lezo-Renteria |  | x | x | [7 empty] | En 1ª fase afectará a vías secundarias suprimiendo el dv nº 12, con corte de tensión en Banda de Mantenimiento. En 2ª fase se retranqueará el dv nº 6, y será necesario corte de fin de semana, pero no se actuará en este desvío hasta verano del 2022, en el que se tramitará un GESTO
ADIF | 2021-6-056 | Brinkola - Irun | ambos | Madrid | Hendaya | 2021 | 2022 |  |  | 2021-10-01 |  | 30/06/2022 |  | 8 meses | - | Sustitución de Hilo de Contacto en las Cercanías de San Sebastián, trayecto Brinkola - Irun |  |  | x | [7 empty] | Banda de Mantenimiento con intervalo adicional. Adjunto GESTO
ADIF | 2021-6-057 | Alegria - Agurain | ambos | Madrid | Hendaya | 2021 | 2022 |  |  | 2021-11-15 |  | mar-22 |  | 3 meses | - | Rehabilitación de la infraestructura del túnel de Txintxetru P.K. 510/080 - 510/619 entre Alegría y Agurain |  |  | x | [7 empty] | Banda de Mantenimiento con intervalo adicional con LTV de 30 km/h hasta que acaben los trabajos
ADIF | 2022-6-001 | Lezama - Artomaña | ambos | Casetas | Bilbao Abando | 2022 | 2022 |  |  | 2022-03-01 |  | 30/06/2022 |  | 3 meses | - | Sustitución de traviesas dañadas por el descarrilamiento de fecha 03/04/2017 del 194/790 al 199/198 entre Lezama y Artomaña. |  |  | x | [7 empty] | Banda de Mantenimiento con intervalo adicional con LTV de 30 km/h mientras duren los trabajos. Pendiente de adjudicación
ADIF | 2022-6-002 | Izarra - Inoso | ambos | Casetas | Bilbao Abando | 2022 | 2022 |  |  | 2022-03-01 |  | jun-22 |  | 3 meses | - | Sustitución de traviesas dañadas por el descarrilamiento de fecha 23/05/2017 del 183/743 al 187/630 entre Izarra e Inoso |  |  | x | [7 empty] | Banda de Mantenimiento con intervalo adicional con LTV de 30 km/h mientras duren los trabajos. Pendiente de adjudicación
ADIF | 2022-6-007 | Estación de Cabezón de PIsuerga | ambos | Madrid | Hendaya | 2022 | 2023 |  |  | 2022-07-01 |  | 15/07/2023 |  | 12 meses | - | Renovación de integral de catenaria en la estación de Cabezón de Pisuerga |  | x | x | [7 empty] | Banda de Mantenimiento Ampliada con posibles LTV de 30/60 kmh. Pendiente de adjudicación
ADIF | 2022-6-008 | Legorreta - Tolosa | ambos | Madrid | Hendaya | 2022 | 2022 |  |  | 2022-04-01 |  | dic-22 |  | 8 meses | - | Sustitución de postes de catenaria entre Legorreta y Tolosa |  |  | x | [7 empty] | Banda de Mantenimiento Ampliada con posibles LTV de 30/60 kmh
ADIF | 2022-6-010 | Orduña - Amurrio | ambos | Casetas | Bilbao Abando | 2022 | 2022 |  |  | 2022-05-01 |  | dic-22 |  | 8 meses | - | Reparación del puente sobre el río Nervión P.K. 212/413 entre Orduña y Amurrio |  | x | x | [7 empty] | Banda de Mantenimiento Ampliada con posibles LTV de 30/60 kmh
ADIF | 2022-6-011 | Zumarraga - Gabiria | ambos | Madrid | Hendaya | 2022 | 2022 |  |  | 2022-05-01 |  | 01/09/2022 |  | 4 meses | - | Reparación por los daños ocasionados por el desprendimiento y descarrilamiento del día 9/12/2021 entre el P.K. 569/600 al 570/200 entre Zumarraga y Gabiria |  | x | x | [7 empty] | Banda de Mantenimiento Ampliada con LTV de 30 km/h para desguarnecido de vía y sustitución de traviesas. Posibles cortes extrarordinarios de fin de semana. Pendiente de tramitación y licitación.
ADIF | 2023-6-001 | Quintana del Puente - Villodrigo | ambos | Madrid | Hendaya | 2023 | 2023 |  |  | 2023-03-01 |  | dic-23 |  | 9 meses | - | Reparación del puente sobre el río Arlanzón I PK 321/285 entre Quintana del Puente y Villodrigo |  | x | x | [7 empty] | Banda de Mantenimiento con intervalo adicional con LTV de 30/60 km/h, según se avance en la obra, que necesitará 3 semanas de corte en cada una de las vías alternativamente. Pendiente de licitación
ADIF | 2023-6-002 | Estación de Ollargan | ambos | Casetas | Bilbao Abando | 2022 | 2023 |  |  | 2022-10-01 |  | 12/12/2023 |  | 13 meses | - | Estabilización de terraplén del 245/100 al 245/433 en la estación de Ollargan. | x | x | x | [7 empty] | Se está redactando el proyecto del terraplén de Ollargan en el PK 245, mediante dos proyectos, uno de estabilización del terraplén mediante inyecciones, en redacción y otro de sustitución de la coronación levantando cada una de las vías, que redactaremos con los lotes de proyectos. Una vez aprobados y licitados, posiblemente en verano de 2023, sería necesario un corte de cada una de las vías de 6 semanas de duración. Este corte sería compatible con el necesario de 3 semanas para impermeabilizar el tablero del viaducto del PK 245. Durante las 3 semanas que dure la impermeabilización de la vía 1 del viaducto, no sería posible acceder al taller de Renfe de Ollargan (el acceso por la cabecera Bidebieta estaría impedido por la obra del terraplén). Si Renfe, no puede estar 3 semanas sin acceder al taller, en el caso de vía 1, los cortes de terraplén y viaducto no serían compatibles y tendrían que hacerse uno detrás de otro, es decir, en 9 semanas. En resumen, en verano de 2023, corte de vía 2 entre Bidebieta y Abando de 6 semanas y de vía 1 de 6 semanas, si Renfe puede prescindir del taller y de 9 si no puede.
ADIF | 2021-3-011 | Mérida - Badajoz (p.k.: 465/300 y 498/300) | Ambas direcciones | Merida | Badajoz | 2021 | 2022 |  |  | 3º trimestre 2022 |  | 4er trimestre 2022 |  | 7 meses |  | Trabajos de ejecución de pantallas de pilotes en la zona de Bifurcación Isla y Bifurcación San Nicolás para conectar la LAV con el FFCC. Actuación también en Montijo | x |  | x | [7 empty] | Tras las TBAs de Isla y Montijo y colocados los desvíos que formarán el PAET de Montijo sobre la Convencional, se levantan las limitaciones existentes. Asimismo, se han finalizado los trabajos de montaje de vía en las diagonales de Montijo 2 e Isla finalizándose Montijo 1 a finales de Enero de 2022. A partir de esa fecha, se comienzan los trabajos en San Nicolas (zona de El Fresnal).
ADIF | 2021-3-041 | Madrid-Badajoz |  | 493/045 |  | 2022 |  |  |  | 2º trimestre 2022 | [5 empty] | PROYECTO DE MODERNIZACION, MEJORA YTRATAMIENTO DE LACIMENTACION DEL PUENTESOBRE EL RIO ALCAZABA,SITUADO EN EL PK 493+045 | [10 empty] | Se realizará tras la puesta servicio la obra de AV
ADIF | 2021-6-018 | Pamplona - Castejón de Ebro | ambos | Altsasu | Castejón de Ebro | 2021 | 2022 |  |  | 2021-05-01 |  | 30-08-2022 |  | 15 meses | - | Construcción de obras de fabricas en el ambito de la emergencia entre el P.K. 130/300 al 146/462 entre Caparroso y Garinoain y actuación Paso Superior AP15. |  |  | x | [7 empty] | Banda de Mantenimiento con intervalo adicional. Se han cosnstruido las obras de drenajes transversales. Actualmente sin LTV. En ejecución. Con previsión de cortes extraordinarios puntuales para la AP15, todavía por concretar.
Note on B52: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on C52: Mario Toma TCR code (ID) in the company's national tool (must be unique). The same ID shall be used for the TCR data update
Note on F52: Mario Toma: Not Null; Value must match a Location stored in the TCR Tool topology data or PLC code of the location
Note on G52: Mario Toma: Not Null; Value must match a Location stored in the TCR Tool topology data or PLC code of the location
Note on Q52: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S52: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T52: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X52: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y52: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z52: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA52: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD52: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ52: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK52: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL52: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM52: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN52: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP52: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ52: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on Y53: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z53: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA53: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AP53: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on C54: Mario Toma TCR code (ID) in the company's national tool (must be unique). The same ID shall be used for the TCR data update
Note on F54: Mario Toma: Not Null; Value must match a Location stored in the TCR Tool topology data or PLC code of the location
Note on G54: Mario Toma: Not Null; Value must match a Location stored in the TCR Tool topology data or PLC code of the location
Note on Q54: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S54: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T54: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X54: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y54: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z54: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA54: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD54: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ54: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK54: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL54: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM54: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN54: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP54: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ54: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on C55: Mario Toma TCR code (ID) in the company's national tool (must be unique). The same ID shall be used for the TCR data update
Note on F55: Mario Toma: Not Null; Value must match a Location stored in the TCR Tool topology data or PLC code of the location
Note on G55: Mario Toma: Not Null; Value must match a Location stored in the TCR Tool topology data or PLC code of the location
Note on Q55: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S55: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T55: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X55: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y55: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z55: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA55: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD55: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ55: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK55: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL55: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM55: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN55: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP55: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ55: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B56: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on C56: Mario Toma TCR code (ID) in the company's national tool (must be unique). The same ID shall be used for the TCR data update
Note on F56: Mario Toma: Not Null; Value must match a Location stored in the TCR Tool topology data or PLC code of the location
Note on G56: Mario Toma: Not Null; Value must match a Location stored in the TCR Tool topology data or PLC code of the location
Note on Q56: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S56: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T56: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X56: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y56: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z56: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA56: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD56: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ56: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK56: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL56: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM56: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN56: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP56: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ56: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B57: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on C57: Mario Toma TCR code (ID) in the company's national tool (must be unique). The same ID shall be used for the TCR data update
Note on F57: Mario Toma: Not Null; Value must match a Location stored in the TCR Tool topology data or PLC code of the location
Note on G57: Mario Toma: Not Null; Value must match a Location stored in the TCR Tool topology data or PLC code of the location
Note on Q57: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S57: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T57: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X57: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y57: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z57: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA57: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD57: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ57: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK57: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL57: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM57: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN57: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP57: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ57: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B58: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on C58: Mario Toma TCR code (ID) in the company's national tool (must be unique). The same ID shall be used for the TCR data update
Note on Q58: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S58: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T58: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X58: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y58: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z58: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA58: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD58: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ58: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK58: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL58: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM58: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN58: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP58: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ58: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B59: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on C59: Mario Toma TCR code (ID) in the company's national tool (must be unique). The same ID shall be used for the TCR data update
Note on Q59: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S59: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T59: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X59: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y59: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z59: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA59: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD59: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ59: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK59: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL59: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM59: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN59: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP59: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ59: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B60: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on C60: Mario Toma TCR code (ID) in the company's national tool (must be unique). The same ID shall be used for the TCR data update
Note on Q60: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S60: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T60: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X60: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y60: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z60: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA60: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD60: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ60: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK60: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL60: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM60: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN60: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP60: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ60: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B61: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on C61: Mario Toma TCR code (ID) in the company's national tool (must be unique). The same ID shall be used for the TCR data update
Note on Q61: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S61: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T61: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X61: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y61: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z61: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA61: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD61: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ61: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK61: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL61: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM61: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN61: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP61: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ61: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B62: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on C62: Mario Toma TCR code (ID) in the company's national tool (must be unique). The same ID shall be used for the TCR data update
Note on Q62: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S62: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T62: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X62: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y62: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z62: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA62: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD62: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ62: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK62: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL62: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM62: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN62: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP62: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ62: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B63: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q63: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S63: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T63: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X63: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y63: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z63: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA63: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD63: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ63: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK63: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL63: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM63: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN63: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP63: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ63: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B64: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q64: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S64: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T64: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X64: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y64: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z64: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA64: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD64: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ64: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK64: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL64: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM64: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN64: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP64: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ64: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B65: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q65: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S65: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T65: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X65: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y65: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z65: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA65: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD65: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ65: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK65: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL65: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM65: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN65: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP65: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ65: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B66: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q66: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S66: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T66: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X66: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y66: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z66: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA66: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD66: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ66: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK66: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL66: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM66: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN66: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP66: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ66: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B67: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q67: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S67: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T67: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X67: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y67: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z67: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA67: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD67: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ67: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK67: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL67: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM67: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN67: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP67: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ67: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B68: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q68: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S68: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T68: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X68: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y68: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z68: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA68: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD68: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ68: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK68: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL68: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM68: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN68: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP68: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ68: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B69: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q69: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S69: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T69: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X69: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y69: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z69: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA69: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD69: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ69: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK69: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL69: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM69: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN69: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP69: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ69: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B70: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q70: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S70: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T70: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X70: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y70: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z70: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA70: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD70: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ70: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK70: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL70: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM70: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN70: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP70: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ70: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B71: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q71: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S71: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T71: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X71: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y71: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z71: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA71: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD71: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ71: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK71: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL71: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM71: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN71: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP71: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ71: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B72: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q72: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S72: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T72: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X72: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y72: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z72: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA72: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD72: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ72: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK72: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL72: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM72: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN72: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP72: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ72: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B73: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q73: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S73: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T73: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X73: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y73: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z73: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA73: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD73: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ73: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK73: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL73: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM73: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN73: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP73: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ73: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B74: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q74: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S74: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T74: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X74: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y74: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z74: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA74: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD74: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ74: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK74: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL74: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM74: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN74: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP74: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ74: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B75: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q75: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S75: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T75: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X75: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y75: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z75: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA75: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD75: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ75: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK75: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL75: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM75: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN75: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP75: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ75: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B76: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q76: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S76: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T76: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X76: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y76: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z76: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA76: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD76: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ76: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK76: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL76: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM76: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN76: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP76: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ76: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B77: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q77: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S77: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T77: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X77: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y77: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z77: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA77: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD77: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ77: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK77: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL77: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM77: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN77: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP77: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ77: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B78: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q78: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S78: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T78: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X78: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y78: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z78: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA78: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD78: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ78: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK78: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL78: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM78: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN78: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP78: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ78: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B79: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q79: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S79: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T79: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X79: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y79: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z79: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA79: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD79: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ79: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK79: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL79: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM79: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN79: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP79: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ79: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B80: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q80: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S80: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T80: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X80: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y80: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z80: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA80: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD80: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ80: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK80: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL80: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM80: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN80: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP80: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ80: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B81: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q81: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S81: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T81: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X81: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y81: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z81: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA81: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD81: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ81: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK81: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL81: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM81: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN81: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP81: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ81: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B82: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q82: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S82: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T82: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X82: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y82: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z82: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA82: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD82: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ82: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK82: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL82: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM82: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN82: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP82: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ82: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B83: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q83: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S83: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T83: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X83: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y83: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z83: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA83: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD83: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ83: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK83: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL83: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM83: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN83: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP83: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ83: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B84: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q84: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S84: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T84: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X84: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y84: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z84: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA84: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD84: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ84: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK84: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL84: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM84: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN84: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP84: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ84: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B85: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q85: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S85: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T85: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X85: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y85: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z85: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA85: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD85: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ85: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK85: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL85: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM85: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN85: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP85: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ85: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B86: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q86: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S86: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T86: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X86: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y86: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z86: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA86: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD86: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ86: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK86: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL86: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM86: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN86: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP86: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ86: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B87: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q87: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S87: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T87: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X87: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y87: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z87: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA87: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD87: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ87: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK87: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL87: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM87: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN87: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP87: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ87: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B88: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q88: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S88: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T88: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X88: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y88: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z88: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA88: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD88: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ88: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK88: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL88: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM88: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN88: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP88: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ88: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B89: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q89: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S89: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T89: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X89: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y89: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z89: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA89: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD89: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ89: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK89: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL89: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM89: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN89: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP89: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ89: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B90: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q90: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S90: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T90: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X90: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y90: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z90: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA90: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD90: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ90: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK90: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL90: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM90: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN90: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP90: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ90: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B91: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q91: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S91: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T91: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X91: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y91: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z91: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA91: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD91: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ91: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK91: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL91: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM91: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN91: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP91: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ91: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B92: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q92: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S92: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T92: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X92: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y92: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z92: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA92: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD92: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ92: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK92: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL92: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM92: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN92: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP92: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on B93: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q93: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S93: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T93: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X93: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y93: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z93: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA93: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD93: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ93: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK93: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL93: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM93: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN93: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP93: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ93: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B94: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q94: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S94: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T94: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X94: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y94: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z94: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA94: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD94: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ94: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK94: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL94: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM94: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN94: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP94: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ94: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B95: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q95: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S95: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T95: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X95: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y95: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z95: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA95: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD95: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ95: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK95: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL95: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM95: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN95: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP95: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ95: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B96: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q96: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S96: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T96: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X96: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y96: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z96: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA96: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD96: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ96: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK96: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL96: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM96: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN96: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP96: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ96: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B97: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q97: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S97: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T97: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X97: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y97: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z97: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA97: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD97: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ97: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK97: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL97: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM97: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN97: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP97: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ97: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B98: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q98: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S98: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T98: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X98: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y98: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z98: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA98: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD98: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ98: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK98: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL98: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM98: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN98: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP98: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ98: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B99: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q99: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S99: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T99: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X99: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y99: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z99: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA99: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD99: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ99: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK99: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL99: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM99: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN99: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP99: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ99: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B100: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q100: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S100: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T100: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X100: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y100: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z100: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA100: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD100: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ100: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK100: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL100: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM100: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN100: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP100: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ100: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B101: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q101: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S101: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T101: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X101: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y101: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z101: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA101: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD101: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ101: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK101: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL101: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM101: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN101: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP101: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ101: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B102: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q102: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S102: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T102: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X102: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y102: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z102: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA102: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD102: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ102: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK102: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL102: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM102: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN102: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP102: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ102: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B103: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q103: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S103: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T103: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X103: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y103: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z103: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA103: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD103: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ103: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK103: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL103: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM103: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN103: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP103: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ103: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B104: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q104: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S104: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T104: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X104: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y104: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z104: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA104: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD104: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ104: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK104: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL104: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM104: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN104: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP104: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ104: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B105: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q105: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S105: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T105: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X105: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y105: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z105: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA105: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD105: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ105: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK105: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL105: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM105: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN105: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP105: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ105: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B106: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q106: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S106: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T106: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X106: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y106: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z106: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA106: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD106: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ106: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK106: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL106: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM106: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN106: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP106: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ106: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B107: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q107: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S107: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T107: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X107: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y107: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z107: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA107: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD107: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ107: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK107: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL107: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM107: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN107: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP107: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ107: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B108: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q108: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S108: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T108: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X108: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y108: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z108: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA108: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD108: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ108: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK108: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL108: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM108: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN108: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP108: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ108: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B109: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q109: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S109: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T109: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X109: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y109: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z109: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA109: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD109: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ109: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK109: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL109: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM109: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN109: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP109: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ109: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B110: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q110: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S110: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T110: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X110: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y110: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z110: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA110: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD110: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ110: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK110: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL110: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM110: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN110: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP110: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ110: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B111: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q111: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S111: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T111: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X111: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y111: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z111: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA111: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD111: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ111: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK111: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL111: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM111: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN111: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP111: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ111: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B112: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q112: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S112: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T112: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X112: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y112: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z112: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA112: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD112: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ112: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK112: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL112: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM112: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN112: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP112: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ112: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B113: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q113: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S113: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T113: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X113: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y113: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z113: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA113: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD113: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ113: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK113: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL113: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM113: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN113: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP113: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ113: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B114: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q114: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S114: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T114: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X114: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y114: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z114: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA114: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD114: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ114: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK114: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL114: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM114: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN114: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP114: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ114: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B115: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q115: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S115: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T115: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X115: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y115: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z115: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA115: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD115: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ115: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK115: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL115: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM115: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN115: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP115: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ115: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B116: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q116: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S116: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T116: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X116: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y116: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z116: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA116: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD116: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ116: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK116: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL116: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM116: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN116: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP116: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ116: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B117: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q117: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S117: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T117: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X117: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y117: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z117: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA117: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD117: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ117: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK117: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL117: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM117: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN117: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP117: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ117: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B118: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q118: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S118: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T118: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X118: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y118: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z118: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA118: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD118: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ118: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK118: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL118: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM118: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN118: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP118: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ118: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B119: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q119: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S119: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T119: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X119: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y119: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z119: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA119: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD119: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ119: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK119: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL119: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM119: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN119: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP119: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ119: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B120: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q120: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S120: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T120: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X120: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y120: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z120: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA120: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD120: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ120: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK120: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL120: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM120: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN120: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP120: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ120: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B121: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q121: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S121: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T121: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X121: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y121: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z121: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA121: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD121: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ121: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK121: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL121: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM121: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN121: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP121: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ121: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B122: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q122: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S122: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T122: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X122: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y122: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z122: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA122: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD122: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ122: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK122: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL122: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM122: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN122: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP122: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ122: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B123: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q123: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S123: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on T123: Mario Toma: Value must be: - if true = LT, ST or LT+ST - if false = blank
Note on X123: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y123: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z123: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA123: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AD123: Mario Toma: In case that TCR must be coordinated with neighboring IMs, UIC code of neighboring IM must be entered. If more IMs have to coordinate TCR then their UIC codes must be comma-separated (,)
Note on AJ123: Mario Toma: Defines the weekly interval of the planned works. e.g. 2 would mean, that the works happen every other week.
Note on AK123: Mario Toma: Percentage (integer) of affected estimated travel volume
Note on AL123: Mario Toma: If border is affected their PLC code could be entered. In the case of more affected border PLC values have to be comma-separated (,)
Note on AM123: Mario Toma: Defines a location within the own network, where the rail traffic shall be rerouted. In the case of more affected border PLC values have to be comma-separated (,)
Note on AN123: Mario Toma: Defines a border, where the rail traffic shall be re-routed. In the case of more affected border PLC values have to be comma-separated (,)
Note on AP123: Mario Toma: Possibity to import link with additional information related to the TCR (web link that will be implemented in the tool for the TCR - Documents tab)
Note on AQ123: Mario Toma: The field is used to mentioned shall the automatic process will be apply to the TCR regarding the Annex VII deadlines (for the automatic promotion) If "Yes", then automatic process inside the TCR Tool will be applied to this TCR. Default value is blank or "No".
Note on B124: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q124: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on Y124: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z124: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA124: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B125: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on Q125: Mario Toma: Not null; Value must be in [continuous, periodical,periodical continuous]
Note on S125: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X125: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y125: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z125: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA125: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B126: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S126: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X126: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y126: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z126: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA126: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B127: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S127: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X127: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y127: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z127: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA127: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B128: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S128: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X128: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y128: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z128: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA128: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B129: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X129: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y129: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z129: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA129: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B130: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X130: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y130: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z130: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA130: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B131: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X131: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y131: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z131: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA131: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B132: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X132: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y132: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z132: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA132: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B133: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X133: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y133: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z133: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA133: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B134: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X134: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y134: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z134: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA134: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B135: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S135: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X135: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y135: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z135: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA135: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B136: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X136: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y136: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z136: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA136: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B137: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X137: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y137: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z137: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA137: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B138: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X138: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y138: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z138: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA138: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B139: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X139: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y139: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z139: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA139: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B140: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X140: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y140: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z140: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA140: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B141: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X141: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y141: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z141: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA141: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B142: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S142: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X142: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y142: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z142: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA142: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B143: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S143: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X143: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y143: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z143: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA143: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B144: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S144: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X144: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y144: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z144: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA144: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B145: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S145: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X145: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y145: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z145: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA145: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B146: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S146: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X146: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y146: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z146: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA146: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B147: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S147: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X147: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y147: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z147: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA147: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B148: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S148: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X148: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y148: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z148: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA148: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B149: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S149: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X149: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y149: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z149: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA149: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B150: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S150: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X150: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y150: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z150: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA150: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B151: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S151: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X151: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y151: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z151: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA151: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B152: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S152: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X152: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y152: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z152: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA152: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B153: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S153: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X153: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y153: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z153: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA153: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B154: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S154: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X154: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y154: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z154: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA154: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B155: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S155: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X155: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y155: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z155: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA155: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B156: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S156: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X156: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y156: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z156: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA156: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B157: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S157: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X157: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y157: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z157: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA157: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B158: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S158: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X158: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y158: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z158: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA158: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B159: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S159: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X159: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y159: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z159: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA159: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B160: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S160: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X160: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y160: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z160: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA160: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B161: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S161: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X161: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y161: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z161: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA161: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B162: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S162: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X162: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y162: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z162: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA162: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B163: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S163: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X163: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y163: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z163: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA163: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B164: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S164: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X164: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y164: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z164: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA164: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B165: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S165: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X165: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y165: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z165: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA165: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B166: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S166: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X166: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y166: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z166: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA166: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B167: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S167: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X167: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y167: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z167: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA167: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B168: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S168: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X168: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y168: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z168: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA168: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B169: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S169: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X169: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y169: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z169: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA169: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B170: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S170: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X170: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y170: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z170: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA170: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B171: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S171: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X171: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y171: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z171: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA171: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B172: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S172: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X172: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y172: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z172: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA172: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B173: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S173: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X173: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y173: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z173: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA173: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B174: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S174: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X174: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y174: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z174: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA174: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B175: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S175: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X175: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y175: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z175: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA175: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B176: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S176: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X176: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y176: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z176: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA176: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B177: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S177: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X177: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y177: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z177: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA177: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B178: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X178: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y178: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z178: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA178: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B179: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X179: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y179: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z179: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA179: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B180: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X180: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y180: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z180: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA180: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B181: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X181: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y181: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z181: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA181: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B182: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X182: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y182: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z182: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA182: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B183: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X183: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y183: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z183: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA183: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B184: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X184: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y184: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z184: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA184: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B185: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X185: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y185: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z185: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA185: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B186: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X186: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y186: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z186: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA186: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B187: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X187: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y187: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z187: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA187: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B188: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X188: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y188: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z188: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA188: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B189: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X189: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y189: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z189: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA189: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B190: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X190: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y190: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z190: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA190: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B191: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X191: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y191: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z191: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA191: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B192: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X192: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y192: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z192: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA192: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B193: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X193: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y193: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z193: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA193: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B194: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X194: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y194: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z194: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA194: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B195: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X195: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y195: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z195: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA195: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B196: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X196: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y196: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z196: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA196: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B197: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X197: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y197: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z197: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA197: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B198: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X198: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y198: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z198: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA198: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B199: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X199: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y199: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z199: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA199: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B200: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X200: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y200: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z200: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA200: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B201: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X201: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y201: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z201: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA201: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B202: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X202: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y202: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z202: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA202: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B203: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X203: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y203: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z203: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA203: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B204: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X204: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y204: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z204: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA204: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B205: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X205: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y205: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z205: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA205: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B206: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X206: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y206: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z206: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA206: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B207: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X207: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y207: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z207: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA207: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B208: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X208: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y208: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z208: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA208: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B209: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X209: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y209: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z209: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA209: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B210: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X210: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y210: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z210: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA210: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B211: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X211: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y211: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z211: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA211: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B212: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X212: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y212: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z212: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA212: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B213: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X213: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y213: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z213: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA213: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B214: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X214: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y214: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z214: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA214: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B215: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X215: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y215: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z215: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA215: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B216: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X216: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y216: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z216: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA216: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B217: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X217: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y217: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z217: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA217: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B218: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X218: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y218: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z218: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA218: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B219: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X219: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y219: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z219: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA219: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B220: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X220: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y220: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z220: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA220: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B221: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X221: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y221: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z221: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA221: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B222: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on X222: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y222: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z222: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA222: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B223: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S223: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X223: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y223: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z223: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA223: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B224: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S224: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X224: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y224: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z224: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA224: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B225: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S225: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X225: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y225: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z225: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA225: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B226: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S226: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X226: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y226: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z226: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA226: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B227: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S227: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X227: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y227: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z227: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA227: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on B228: Mario Toma: Not null; Value must match the name of an Organisation Units defined in the TCR-Tool or organization UIC code
Note on S228: Mario Toma: Value must be: - if true = (T or X) - if false = blank
Note on X228: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Y228: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on Z228: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not
Note on AA228: Mario Toma: This value present an array of 3 values (freight trains, long distance trains, short distance trains). Values must be comma-separated (,). - if true = X values e.g. (X,,X) means that freight trains and short distance trains are cancelled and long distance trains are not cancelled - if false = empty or ,, e.g. ,, means that trains are not cancelled or e.g. X,X, means that freight trains and long distance trains are cancelled and short distance trains are not